## Sheet1
ITP Discipline |  | Civil Concrete Works |  | Project Area | Donaldson Road. Kwinana
Project Title |  | Donaldson Road Delivery Station Upgrade |  | Revision | A
Primero Document No. |  | 06705-ITP-CV-001 |  | Date | 2018-05-16
Client |  | APA Group |  | Prepared | R. O’Callaghan
Client Document No. |  |  |  | Approved | S. Lamond
H = HOLD POINT |  | V = VISUAL INSPECTION | R = REVIEW | D = DIMENSIONAL INSPECTION |  | WR = WITNESS @ RANDOM
W = WITNESS POINT |  | M = MONITOR ON A RANDOM BASIS | A = APPROVE | S = SUBMIT DOCUMENT TO CLIENT
REF | INSPECTION AND TEST ACTIVITY | APPLICABLE DOCUMENT OR PROCEDURE ETC. | ACCEPTANCE CRITERIA | VERIFYING DOCUMENT | INSPECTION AND VERIFICATION
[5 empty] | Primero |  | Client |  | 3RD Party Inspection
[5 empty] | Activity | Signature | Activity | Signature | Activity | Signature
1 | SPECIFICATIONS
1.1 | Review Scope of Work | 18036-SOW-M-0003 | Not Applicable | Contract Document | R |  | R
1.2 | Review Design | Packaged Equipment Specification | 18036-SOW-M-0003 | Design Approval, VDS | S |  | R
1.3 | Review Drawings | AFC Drawings | Drawings | AFC Drawings | S |  | R
2 | EQUIPMENT
2.1 | Inspect Vendor Mechanical Equipment | Vendor Documentation | Compliance for Manufacture | Vendor MDR / Documentation | W |  | WR / R
3 | PREPARE FOR INSTALLATION
3.1 | Dimensional check of structural steelwork prior to installation | Structural Steel Erection 530-SP-S-0004 | Vendor Documents and Structural Drawings | General Arrangement Drawings | V |  | R
3.2 | Review Previous Documentation of tension inspection of Bolts on Structural Steel work | Structural Steel Erection 530-SP-S-0004 | 530-SP-S-0004 | Bolt Torque Record 06705-ITR-ST-101 | R |  | R
4 | INSTALL MECHANICAL EQUIPMENT
4.1 | Install equipment onto new structural steelwork | Vendor supplied documents and drawings | Vendor Specification and drawings | Inspection and Test Records | M |  | R
4.2 | Confirm Elevations and Centre lines of Mechanical Equipment | Packaged Equipment Specification | Vendor Documents | As-built Drawings | H |  | W
4.3 | Carry out tension inspection of hold down bolts | Structural Steel Erection 530-SP-S-0004 | Vendor Documents | Bolt Torque Record 06705-ITR-ST-101 | S |  | R
4.4 | Bolt up piping and instrumentation | Piping ITP-PP-001 | 530-SP-P-0002, Vendor Documents | Alignment Report (where applicable), 06705-ITR-PP-101 | S |  | R
4.5 | Preservation | Packaged Equipment Specification | Vendor Documents | 06705-ITR-ME-103 | H |  | W
4.6 | Pre-commissioning (as applicable) | Commissioning test plan | Commissioning test plan | Commissioning Test Report | H |  | H
5 | PREPARATION FOR HANDOVER
5.1 | Touch up painting | Coating Subcontractor Procedure, Coating Subcontractor ITP | 530-SP-M-9602 | Coatings Inspection Report (where required) | M |  | R
5.2 | Prepare all documentation for handover and sign off | Contract Document | 18036-SOW-M-0003 | All check sheets referenced, ITP to be signed off, As Built Drawings completed. | S |  | A
3 | VERIFICATION
3.1 | Punchlisting | AFC Drawings, 18036-SOW-M-0003 | AFC Drawings, 18036-SOW-M-0003 | Completed Client Punchlist | H |  | H