## ITP-000
|  |  | INSPECTION AND TEST PLAN | [6 empty] | ITP No:
CONTRACTOR:
|  |  | ITP DESCRIPTION: | [6 empty] | CLIENT:
|  |  | FMG Solomon AN Bulk Storage Facility - _____________ | [6 empty] | Contract Number:
PRINCIPAL:
Reference Codes, Specifications & Drawing | [5 empty] | References and Verifying Documents | [5 empty] | Nomenclature
No. |  |  | Title |  |  | Doc. No. |  | Title |  |  |  | Symbol | Description
[12 empty] | I | In House
[12 empty] | S | Subcontractor
[12 empty] | W | Witness
[12 empty] | H | Hold
[12 empty] | SV | Surveillance
[12 empty] | R | Review
Revision |  | Description |  |  |  | Date | Prepared By |  |  |  | Approved By
|  |  | INSPECTION AND TEST PLAN | [6 empty] | ITP No:
CONTRACTOR:
|  |  | ITP DESCRIPTION: | [6 empty] | CLIENT:
|  |  | FMG Solomon AN Bulk Storage Facility - ____________ | [6 empty] | Contract Number:
PRINCIPAL:
Task |  |  |  | Location Code (I or S) | Controlling Procedure or Instruction | Acceptance Criteria | Verifying Documents |  | Inspection Requirements (See Legend) |  |  |  |  | Contractor Signature
No. | Probable Date | Description | [6 empty] | Contractor | Engineer |  |  | Client
[10 empty] | Insp | Engineer | Signature
1

## ITP-001 Earthworks
|  |  | INSPECTION AND TEST PLAN | [6 empty] | ITP No:
CONTRACTOR:
|  |  | ITP DESCRIPTION: | [6 empty] | CLIENT:
|  |  | FMG Solomon AN Bulk Storage Facility - Earthworks | [6 empty] | Contract Number:
PRINCIPAL:
Reference Codes, Specifications & Drawing | [5 empty] | References and Verifying Documents | [5 empty] | Nomenclature
No. |  |  | Title |  |  | Doc. No. |  | Title |  |  |  | Symbol | Description
[12 empty] | I | In House
[12 empty] | S | Subcontractor
[12 empty] | W | Witness
[12 empty] | H | Hold
[12 empty] | SV | Surveillance
[12 empty] | R | Review
Revision |  | Description |  |  |  | Date | Prepared By |  |  |  | Approved By
|  |  | INSPECTION AND TEST PLAN | [6 empty] | ITP No:
CONTRACTOR:
|  |  | ITP DESCRIPTION: | [6 empty] | CLIENT:
|  |  | FMG Solomon AN Bulk Storage Facility - Earthworks | [6 empty] | Contract Number:
PRINCIPAL:
Task |  |  |  | Location Code (I or S) | Controlling Procedure or Instruction | Acceptance Criteria | Verifying Documents |  | Inspection Requirements (See Legend) |  |  |  |  | Contractor Signature
No. | Probable Date | Description | [6 empty] | Contractor | Engineer |  |  | Client
[10 empty] | Insp | Engineer | Signature
1 | DOCUMENTS REQUIRING APPROVAL
1.1 |  | Submission of Applicable Civil Works Procedure(s) |  |  | Standard Engineering Specification for Drainage and Flood Protection | Approve Specification | 100-SP-CI-0004
[5 empty] | Standard Engineering Specification for Site Earthworks Construction | Approve Specification | 100-SP-CI-0007
1.2 |  | Preparation and Submission of Civil Works Method Statements |  |  | Method Statements for Earthworks | Prepare and Submit Method Statements
2 | SITE PREPARATION
2.1 |  | Setting out |  |  | Standard Engineering Specification for Site Earthworks Construction | Comply to Specification | 100-SP-CI-0007 Section 5.1
2.2 |  | Extent of Clearing |  |  | Standard Engineering Specification for Site Earthworks Construction | Comply to Specification | 100-SP-CI-0007 Section 5.2
2.3 |  | Site Inspection |  |  | Standard Engineering Specification for Site Earthworks Construction | Comply to Specification | 100-SP-CI-0007 Section 5.3
2.4 |  | Site Clearing |  |  | Standard Engineering Specification for Site Earthworks Construction | Comply to Specification | 100-SP-CI-0007 Section 5.4
2.5 |  | Grubbing and Refilling |  |  | Standard Engineering Specification for Site Earthworks Construction | Comply to Specification | 100-SP-CI-0007 Section 5.5
2.6 |  | Topsoil Stripping |  |  | Standard Engineering Specification for Site Earthworks Construction | Comply to Specification | 100-SP-CI-0007 Section 5.6
2.7 |  | Regrowth |  |  | Standard Engineering Specification for Site Earthworks Construction | Comply to Specification | 100-SP-CI-0007 Section 5.7
2.8 |  | Excess Clearing |  |  | Standard Engineering Specification for Site Earthworks Construction | Comply to Specification | 100-SP-CI-0007 Section 5.8
3 | EXCAVATION

## Template
CLIENT: |  | FMG Solomon |  |  |  | DOCUMENT |  | I.T.P. | Rev 0 |  | Page 1 of 5
PROJECT: |  | CLIENT REFERENCE No: |  |  |  | SCOPE OF ITP: |  |  | Primero Job No: |  |  | 2704
Prepared By:
|  | Final Release/Responsibility by: | [6 empty] | Primero Doc No.: |  |  | 02704-ITP-CI-001
|  | CLIENT APPROVAL | [6 empty] | Client Doc No.:
REF | INSPECTION AND TEST ACTIVITY |  | APPLICABLE DOCUMENT OR PROCEDURE ETC. |  | ACCEPTANCE CRITERIA | VERIFYING DOCUMENT |  |  | INSPECTION AND VERIFICATION
[9 empty] | Primero |  | Client |  | 3rd Party Inspection
[9 empty] | ACT. | SIG. | ACT. | SIG. | ACT. | SIG.
1
LEGEND |  | H = HOLD POINT |  | ACT = ACTIVITY |  |  | R/A = REVIEW & APPROVE DOC. |  |  |  | D = DIMENSIONAL INSPECTION
|  | S = SUBMIT DOCUMENT TO CLIENT |  | W = WITNESS POINT |  |  | V = VISUAL INSPECTION |  |  |  | V/S = VERIFYING SIGNATURE
|  | M = MONITOR ON A RANDOM BASIS |  | W @ R = WITNESS @ RANDOM |  |  | A = APPROVE |  |  |  | R & C = REVIEW & COMMENT
CLIENT: |  | FMG Solomon |  |  |  | DOCUMENT |  | I.T.P. | Rev 0 |  | Page 1 of 5
PROJECT: |  | CLIENT REFERENCE No: |  |  |  | SCOPE OF ITP: |  |  | Primero Job No: |  |  | 2704
Prepared By:
|  | Final Release/Responsibility by: | [6 empty] | Primero Doc No.: |  |  | 02704-ITP-CI-001
|  | CLIENT APPROVAL | [6 empty] | Client Doc No.:
REF | INSPECTION AND TEST ACTIVITY |  | APPLICABLE DOCUMENT OR PROCEDURE ETC. |  | ACCEPTANCE CRITERIA | VERIFYING DOCUMENT |  |  | INSPECTION AND VERIFICATION
[9 empty] | Primero |  | Client |  | 3rd Party Inspection
[9 empty] | ACT. | SIG. | ACT. | SIG. | ACT. | SIG.
LEGEND |  | H = HOLD POINT |  | ACT = ACTIVITY |  |  | R/A = REVIEW & APPROVE DOC. |  |  |  | D = DIMENSIONAL INSPECTION
|  | S = SUBMIT DOCUMENT TO CLIENT |  | W = WITNESS POINT |  |  | V = VISUAL INSPECTION |  |  |  | V/S = VERIFYING SIGNATURE
|  | M = MONITOR ON A RANDOM BASIS |  | W @ R = WITNESS @ RANDOM |  |  | A = APPROVE |  |  |  | R & C = REVIEW & COMMENT
INSPECTION AND TEST PLAN 02704-ITP-CI-001
INSPECTION AND TEST PLAN 02704-ITP-CI-001

## Civil
CLIENT: |  | FMG Solomon |  |  |  | DOCUMENT |  | I.T.P. | Rev 0 |  | Page 1 of 5
PROJECT: |  | CLIENT REFERENCE No: |  |  |  | SCOPE OF ITP: |  | Civil | Primero Job No: |  |  | 2704
|  | Prepared By: |  | Peter Kroeger
|  | Final Release/Responsibility by: | [6 empty] | Primero Doc No.: |  |  | 02704-ITP-CI-002
|  | CLIENT APPROVAL | [6 empty] | Client Doc No.:
REF | INSPECTION AND TEST ACTIVITY |  | APPLICABLE DOCUMENT OR PROCEDURE ETC. |  | ACCEPTANCE CRITERIA | VERIFYING DOCUMENT |  |  | INSPECTION AND VERIFICATION
[9 empty] | Primero |  | Client |  | 3rd Party Inspection
[9 empty] | ACT. | SIG. | ACT. | SIG. | ACT. | SIG.
1 | Planning
1.1 | Quality Management Plan |  |  |  | Submitted & Approved
1.2 | Construction Drawings |  |  |  | AFC Drawings
1.3 | Safe Work Instructions |  |  |  | Submitted & Approved
1.4 | Approval of Concrete Mix Design |  | AFC Drawings |  | AS-1379 | NATA Test Results
Trial Mix
2 | Formwork Installation
2.1 | Confirm formwork is secured to |  | 100-SP-CI-0003 |  | AFC Drawings | ITR
| correct lines and levels |  |  |  | Formwork Drawings
AS-3610
2.2 | Survey formwork to ensure within |  | 100-SP-CI-0003 |  | AFC Drawings | ITR
| tolerance |  |  |  | AS-3610
2.3 | Inspect formwork to ensure |  | 100-SP-CI-0003 |  | Formwork Drawings | ITR
| compliance to design |  |  |  | AFC Drawings
3 | Reinforcment Installation
3.1 | Reinforcement is processed, bent |  | 100-SP-CI-0003 |  | AS-4671 | ISO 9001
| to specifications |  |  |  |  | ACRS Certificates
Mill Certificates
3.2 | Reinforcement is bundled, tagged |  | 100-SP-CI-0003 |  | AS-4671 | Delivery Schedules
and stored to specifications
3.1 | Ensure all materials are clean, cut and |  | 100-SP-CI-0003 |  | AFC Drawings | ITR
| bent to schedules |  |  |  | AS-4671
3.2 | Confirm all reinforcement is in place |  | 100-SP-CI-0003 |  | AFC Drawings | ITR
and secured
3.3 | Check cover is in compliance to |  | 100-SP-CI-0003 |  | AFC Drawings | ITR
specifications and drawings
3.4 | Ensure all supports, chairs, blocks are |  | 100-SP-CI-0003 |  | AFC Drawings | ITR
in place
3.5 | Verify splicing is as per drawings and |  | 100-SP-CI-0003 |  | AFC Drawings | ITR
| specifications |  |  |  | AS-3600
3.6 | Check reinforcement is sufficiently |  | 100-SP-CI-0003 |  | AFC Drawings | ITR
fixed
LEGEND |  | H = HOLD POINT |  | ACT = ACTIVITY |  |  | R/A = REVIEW & APPROVE DOC. |  |  |  | D = DIMENSIONAL INSPECTION
|  | S = SUBMIT DOCUMENT TO CLIENT |  | W = WITNESS POINT |  |  | V = VISUAL INSPECTION |  |  |  | V/S = VERIFYING SIGNATURE
|  | M = MONITOR ON A RANDOM BASIS |  | W @ R = WITNESS @ RANDOM |  |  | A = APPROVE |  |  |  | R & C = REVIEW & COMMENT
CLIENT: |  | FMG Solomon |  |  |  | DOCUMENT |  | I.T.P. | Rev 0 |  | Page 1 of 5
PROJECT: |  | CLIENT REFERENCE No: |  |  |  | SCOPE OF ITP: |  |  | Primero Job No: |  |  | 2704
Prepared By:
|  | Final Release/Responsibility by: | [6 empty] | Primero Doc No.: |  |  | 02704-ITP-CI-001
|  | CLIENT APPROVAL | [6 empty] | Client Doc No.:
REF | INSPECTION AND TEST ACTIVITY |  | APPLICABLE DOCUMENT OR PROCEDURE ETC. |  | ACCEPTANCE CRITERIA | VERIFYING DOCUMENT |  |  | INSPECTION AND VERIFICATION
[9 empty] | Primero |  | Client |  | 3rd Party Inspection
[9 empty] | ACT. | SIG. | ACT. | SIG. | ACT. | SIG.
4 | Embedments
4.1 | Embedments are to specifications, |  | 100-SP-CI-0003 |  | AFC Drawings | Vendor's ITP
| HD bolts, cast in angles, plates and |  |  |  | AS-4100 | Mill Certificates
| ferrules |  |  |  |  | WPQ's, WP's
Galvanising reports
Material reports
ITR
4.2 | Lifting anchors and brace points |  | Approved engineered |  | AS-3850 | Manufacturer's report
|  |  | shop drawings |  | AS-3600 | Lifting engineered design
ITR
4.3 | Placement of embedment items are |  | 100-SP-CI-0003 |  | AFC Drawings | ITR
to specifications and drawings
4.4 | Final visual inspection of all |  | 100-SP-CI-0003 |  | AFC Drawings | ITR
embedments
4.5 | Final pre pour survey of embedment |  | 100-SP-CI-0003 |  | Survey Report | ITR
items placement to ensure within
tolerance
5 | Concrete Placement
5.1 | Correct Mix Code Delivered |  | 100-SP-CI-0003 |  | AFC Drawings | Batch Docket
Trial Mix
5.2 | Concrete Testing - Temperture, Slump |  | 100-SP-CI-0003 |  | AS-1012 | Field Testing Sheet
| Strength |  |  |  | AS-1379 | NATA Test Results
5.3 | Concrete placement |  | 100-SP-CI-0003 |  | AS-3600 | ITR
AFC Drawings
5.4 | Construction Joints |  | 100-SP-CI-0003 |  | AS-3600 | ITR
AFC Drawings
5.5 | Compaction |  | 100-SP-CI-0003 |  |  | ITR
5.6 | Curing |  | 100-SP-CI-0003 |  | AS-3799 | ITR
Manufacture's TDS
5.7 | Inspect concrete surfaces after |  | 100-SP-CI-0003 |  | AS3600 | ITR
formwork removal
5.8 | Concrete Repairs |  | 100-SP-CI-0003 |  | Approved Concrete | ITR
Repair Methodology
6 | Inspection
6.1 | Survey and issue as built of |  | 100-SP-CI-0003 |  | AFC Drawings | Survey Reports
completed structure
7 | Close Out Documentation
7.1 | Compile and submit all signed QA |  | 100-SP-CI-0003 |  |  | MDR
documentation
LEGEND |  | H = HOLD POINT |  | ACT = ACTIVITY |  |  | R/A = REVIEW & APPROVE DOC. |  |  |  | D = DIMENSIONAL INSPECTION
|  | S = SUBMIT DOCUMENT TO CLIENT |  | W = WITNESS POINT |  |  | V = VISUAL INSPECTION |  |  |  | V/S = VERIFYING SIGNATURE
|  | M = MONITOR ON A RANDOM BASIS |  | W @ R = WITNESS @ RANDOM |  |  | A = APPROVE |  |  |  | R & C = REVIEW & COMMENT
INSPECTION AND TEST PLAN 02704-ITP-CI-001
INSPECTION AND TEST PLAN 02704-ITP-CI-001