## ITP-001
ITP Number: | 02707--ITP-QA-001 | Client Contract Number: | CC15OP0003 | Contract Item Number:
Revision Number: | 0 | Contractor Approval: | N/A | Equipment Numbers: | DF1-DF5 AN Shed Doors
Contractor: | Primero Group | Description of Service: | Civil, Structural & Mechanical Site Installation
Works Locations: | Site - FMG Christmas Creek - AN Facility
Task Number | Task Description | Location | Controlling Procedure or Instruction | Acceptance Criteria | Verifying Documents | Inspection Requirements
[6 empty] | Primero | Signature | FMG | Signature
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | DESIGN/SPECIFICATIONS
1.1 | Review AFC Drawings | AN Shed Christmas Creek | AFC Drawings | Client Approved AFC Drawings | Client Approved AFC drawings | W |  | R, S
2 | APPROVALS
2.1 | Submit Project Documentation, Methodology, ITP | AN Shed Christmas Creek | AFC Drawings | AFC Drawings | Approved ITP, Procedures | H |  | R, A
3 | MATERIALS
3.1 | Inspect materials upon mobilisation/delivery | AN Shed Christmas Creek | AFC Drawings | AFC Drawings, Fabrication Drawings | Delivery Dockets, line lists | W |  | S, R
3.2 | Check materials for imperfections/damage | AN Shed Christmas Creek | AFC Drawings | Visual Inspection | Endorsed Material Certificates | W |  | S, R
3.3 | Check supply of vendor equipment for completeness | AN Shed Christmas Creek | AFC Drawings | Visual Inspection | Client Supply List & Delivery Docket | W |  | S, R
4 | CIVIL | I
4.1 | Existing Foundations/Complete Dimensional checks | AN Shed Christmas Creek | AFC Drawings | Visual Inspection | Visual Inspection | W |  | S
4.2 | Verify approved Construction Methodology for Demolition of Concrete | AN Shed Christmas Creek | AFC Drawings | AFC drawings, and Methodology | Approved JHA and method for demolition | H |  | R, A
4.3 | Rail Installation/Dimensional checks | AN Shed Christmas Creek | AFC Drawings | AFC Drawings | Field Inspection, Door Crane Rail Installation 02707-ITR-ME-001 | H |  | A
4.4 | Grouting | AN Shed Christmas Creek | AFC Drawings | AFC Drawings | Field Inspection, Grouting Checklist 02707-ITR-ME-003 | S, R |  | S
5 | STRUCTURAL | I
5.1 | Verify Approved Construction Methodology for Removal of Doors | AN Shed Christmas Creek | Approved Construction Methodolgy | AFC drawings, Methodology/Client Approval | Approved Methodolgy and JHA | H |  | R, A
5.2 | Review appropriate Erection method of Structural Steel | AN Shed Christmas Creek | Client Specification 100-SP-ST-0002, JHA for structural steel installation | Australian Standards and Regulations / AFC Drawings, Client Specification 100-SP-ST-0002 | Approved JHA for Installation of Structural Steel, AFC Drawings, Client Specification | R |  | R
5.3 | Weld Procedure(WPS) & Weld Procedure Qualifications (WPQR) | AN Shed Christmas Creek | WPS, WPQR | AS 1554.1 & AS 1554.6 | Approved WPS, WPQR | R |  | A
5.4 | Structural steel installed and checked | AN Shed Christmas Creek | AFC Drawings, Client Specification 100-SP-ST-0002 | AFC Drawings, Client Specification 100-SP-ST-0002, Bolt tightening to AS 4100 | Visual Inspection and Measurement, Structural Steel Erection Checklist 02707-ITR-ME-005 | W |  | S
5.5 | Non-Destructive Testing (NDT) of Welds | AN Shed Christmas Creek | Client Specification 100-SP-ST-0001 | Client Specification 100-SP-ST-0001 | NATA Test reports | I, R |  | S, R
6 | MECHANICAL INSTALLATION
6.1 | Check door mechanisms have been assembled correctly upon delivery | AN Shed Christmas Creek | AFC Drawings | Visual Inspection | Client Approved AFC drawings | W |  | S, R
6.2 | Verify Approved Construction Methodology for Installation of Rack & Pinion & Chain/Sprocket Drives | AN Shed Christmas Creek | AFC Drawings, Approved Construction Methodolgy | AFC drawings, Methodology/Client Approval | Approved Methodolgy and JHA | H |  | R, A
6.3 | Drive/Wheel Installation/Dimensional Checks | AN Shed Christmas Creek | AFC Drawings, Approved Construction Methodolgy | Visual Inspection | Client Approved AFC drawings | W |  | S
6.4 | Commissioning of Doors/Drives | AN Shed Christmas Creek | AFC Drawings, Approved Construction Methodolgy | Visual Inspection | Client Acceptance | W |  | S
7 | SURFACE TREATMENT (TOUCH UPS)
7.1 | Protect surfaces not requiring treatment, e.g. nameplates. machined surfaces | AN Shed Christmas Creek | Client Specification 100-SP-ST-0004_3 | Client Specification 100-SP-ST-0004_3 | Visual inspection | R |  | S
7.2 | Check surface cleaning, NDT requirements on the items prior to painting as per specification | AN Shed Christmas Creek | Client Specification 100-SP-ST-0004_3 | Client Specification 100-SP-ST-0004_3 | Visual Inspection, Structural Steel Erection Checklist 02707-ITR-ME-005 | W |  | S
7.3 | Monitor atmospheric conditions daily for Temperature as per Manufacturers specifications | AN Shed Christmas Creek | Dulux Protective Coatings System Specifications for Christmas Creek Structural Steel Maintenance | Dulux Protective Coatings System Specifications for Christmas Creek Structural Steel Maintenance | Bureau of Meteorology Data | R |  | S
7.4 | Ensure the items to be painted are adequately laid out and masked as needed | AN Shed Christmas Creek | Client Specification 100-SP-ST-0004_3 | Client Specification 100-SP-ST-0004_3 | Visual Inspection | W |  | S
7.5 | Check use of correct paint to manufacturers recommendations | AN Shed Christmas Creek | Dulux Protective Coatings System Specifications for Christmas Creek Structural Steel Maintenance | Dulux Protective Coatings System Specifications for Christmas Creek Structural Steel Maintenance | Visual Inspection, Manufacturers reccomendations | R |  | S, R, H
8 | FINAL INSPECTION ON COMPLETION
8.1 | Carry out final inspection Verification / clearance of punch list | AN Shed Christmas Creek | AFC Drawings, ITR's | Approved AFC Drawings, ITR's | Punchlists, Field Inspection Checklist, Inspection release certificate | R |  | S, H
9 | FINALISE DOCUMENTATION
9.1 | Progressively check all test reports are correct. | AN Shed Christmas Creek | Client Specifications | Client Specifications | Reviewed and Approved ITR's | R |  | R
9.2 | Sign off Inspection & Test Plan | AN Shed Christmas Creek | Client Specifications | AFC Drawings, Visual Inspection, ITR's | Completed ITP | H |  | R, W
9.3 | MDR to be progressively compiled and submitted to client for final approval. | AN Shed Christmas Creek | Client Specifications | Scope of Work | Completed MDR | H |  | R, A
GLOSSARY
|  | CONTROL | PRIMERO | FMG
|  | APPROVAL | FMG Approval required of the applicable activity or result from an activity
|  | HOLD | A critical operation or process beyond which work shall not proceed without attendance of the Primero representative | A critical operation or process beyond which work shall not proceed without attendance of the FMG representative
|  | REVIEW | Review of documentation providing objective evidence of the suppliers compliance with contractual requirements | Review of documentation providing objective evidence of the suppliers compliance with contractual requirements
|  | WITNESS | A work activity to be witnessed by the Primero representative. The activity may proceed without the witness only with the prior written approval by the Primero representative | A work activity to be witnessed by the FMG representative. The activity may proceed without the witness only with the prior written approval by the BP representative
|  | SURVEILANCE | Periodic surveillance by the Primero representative. No specific notification is required and the activity may proceed when the Primero representative is not present | Periodic surveillance by the FMG representative. No specific notification is required and the activity may proceed when the FMG representative is not present
|  | INSPECTION | A stage in the works where inspection and or testing is performed by personnel whose responsibility is to determine the acceptability of products or services and to record inspection and test data