## ITP-REG
INSPECTION AND TEST PLAN (ITP) REGISTER
|  | CLIENT : | Fortescue Metals Group
|  | PROJECT : | Solomon Bulk Ammonium Nutrate Storage Facility
|  | PROJECT No : | 02704
|  | SITE : | Solomon
|  | LAST UPDATED : | 2014-10-17
ITR No. | Title |  |  | Originator | Date Issued | Date Completed
ITP-001 | EARTHWORKS |  |  | Darren Duthie | 2014-10-17 | 2014-10-17
ITP-002 | CIVIL WORKS |  |  | Darren Duthie | 2014-10-17 | 2014-10-17
ITP-003

## ITP-001
CLIENT: |  | FMG Solomon |  |  |  |  | DOCUMENT |  | I.T.P. | Rev A |  | Page 1 of 3
PROJECT: |  | CLIENT REFERENCE No: |  |  |  |  | SCOPE OF ITP: |  | Earthworks | Primero Job No: |  |  | 2704
|  | Prepared By: |  |  | Peter Kroeger
|  | Final Release/Responsibility by: | [7 empty] | Primero Doc No.: |  |  | 02704-ITP-CI-001
|  | CLIENT APPROVAL | [7 empty] | Client Doc No.:
REF | INSPECTION AND TEST ACTIVITY |  |  | APPLICABLE DOCUMENT OR PROCEDURE ETC. |  | ACCEPTANCE CRITERIA | VERIFYING DOCUMENT |  |  | INSPECTION AND VERIFICATION
[10 empty] | Primero |  | Client |  | 3rd Party Inspection
[10 empty] | ACT. | SIG. | ACT. | SIG. | ACT. | SIG.
1 | Preceding Tasks
1.1 | Site Handover |  |  | Handover Letter |  | Sign and Approve Handover Letter | TO BE CONSTRUCTED |  |  | H |  | H
1.2 | Specification Sign Off |  |  | 100-SP-CI-0007 100-SP-CI-0004 100-SP-CI-0002 |  | Approval of Specification Documents | TO BE CONSTRUCTED |  |  | H |  | H
1.3 | Bulk Compaction Testing Sign Off |  |  | Bulk Compaction Test Results |  | Approval of Bulk Compaction Test Results | TO BE CONSTRUCTED |  |  | H |  | H
4 | Material Compliance and Certification
4.1 | Crushed Rock |  |  | 100-SP-CI-0007 |  | Comply with Specifications and Standards |  |  |  | W |  | M
4.2 | Fill Materials |  |  | 100-SP-CI-0007 AS 1289 AS 1152 AS 1141 |  | Comply with Specifications and Standards |  |  |  | W |  | M
5 | Excavation
5.1 | Approved Drawings |  |  | AFC Drawings |  | Approval of Drawings | 02704-ITR-001 |  |  | H |  | M
5.2 | Approved Specification |  |  | 100-SP-CI-0007 |  | Approval of Specification | 02704-ITR-001 |  |  | H |  | H
6 | Backfill
6.1 | Compaction Thickness Layers |  |  | 100-SP-CI-0007 |  | Comply with Specifications | 02704-ITR-001 |  |  | W |  | M
7 | Compaction
7.1 | Compaction Thickness Layers |  |  | 100-SP-CI-0007 |  | Comply with Specifications | 02704-ITR-001 |  |  | W |  | M
LEGEND |  | H = HOLD POINT |  |  | ACT = ACTIVITY |  |  | R/A = REVIEW & APPROVE DOC. |  |  |  | D = DIMENSIONAL INSPECTION
|  | S = SUBMIT DOCUMENT TO CLIENT |  |  | W = WITNESS POINT |  |  | V = VISUAL INSPECTION |  |  |  | V/S = VERIFYING SIGNATURE
|  | M = MONITOR ON A RANDOM BASIS |  |  | W @ R = WITNESS @ RANDOM |  |  | A = APPROVE |  |  |  | R & C = REVIEW & COMMENT
CLIENT: |  | FMG Solomon |  |  |  |  | DOCUMENT |  | I.T.P. | Rev A |  | Page 2 of 3
PROJECT: |  | CLIENT REFERENCE No: |  |  |  |  | SCOPE OF ITP: |  | Earthworks | Primero Job No: |  |  | 2704
|  | Prepared By: |  |  | Peter Kroeger
|  | Final Release/Responsibility by: | [7 empty] | Primero Doc No.: |  |  | 02704-ITP-CI-001
|  | CLIENT APPROVAL | [7 empty] | Client Doc No.:
REF | INSPECTION AND TEST ACTIVITY |  |  | APPLICABLE DOCUMENT OR PROCEDURE ETC. |  | ACCEPTANCE CRITERIA | VERIFYING DOCUMENT |  |  | INSPECTION AND VERIFICATION
[10 empty] | Primero |  | Client |  | 3rd Party Inspection
[10 empty] | ACT. | SIG. | ACT. | SIG. | ACT. | SIG.
8 | Tolerance of Earthworks
8.1 | Surface Levels |  |  | 100-SP-CI-0007 Section 15 |  |  | 02704-ITR-001 |  |  | W |  | M
8.2 | Grade Condition |  |  | 100-SP-CI-0007 Section 15 |  |  | 02704-ITR-001 |  |  | W |  | M
8.3 | Finishing Tolerances |  |  | 100-SP-CI-0007 Section 15 |  |  | 02704-ITR-001 |  |  | W |  | H
9 | Earthworks Testing
9.1 | Instrument Calibration |  |  | 100-SP-CI-0007 Section 16.3 |  |  | Calibration Certificate |  |  | W |  | W
9.2 | Acceptance Testing |  |  | 100-SP-CI-0007 Section 13.3 100-SP-CI-0007 Section 16.4 |  |  | Compaction Certificate |  |  | W |  | M
9.3 | Frequency of Testing |  |  | 100-SP-CI-0007 Section 13.4 100-SP-CI-0007 Appendix 1 & 2 AS3798-2007 Table 8.1 |  |  | NATA Certificate |  |  | W |  | M
LEGEND |  | H = HOLD POINT |  |  | ACT = ACTIVITY |  |  | R/A = REVIEW & APPROVE DOC. |  |  |  | D = DIMENSIONAL INSPECTION
|  | S = SUBMIT DOCUMENT TO CLIENT |  |  | W = WITNESS POINT |  |  | V = VISUAL INSPECTION |  |  |  | V/S = VERIFYING SIGNATURE
|  | M = MONITOR ON A RANDOM BASIS |  |  | W @ R = WITNESS @ RANDOM |  |  | A = APPROVE |  |  |  | R & C = REVIEW & COMMENT
CLIENT: |  | FMG Solomon |  |  |  |  | DOCUMENT |  | I.T.P. | Rev A |  | Page 3 of 3
PROJECT: |  | CLIENT REFERENCE No: |  |  |  |  | SCOPE OF ITP: |  | Earthworks | Primero Job No: |  |  | 2704
|  | Prepared By: |  |  | Peter Kroeger
|  | Final Release/Responsibility by: | [7 empty] | Primero Doc No.: |  |  | 02704-ITP-CI-001
|  | CLIENT APPROVAL | [7 empty] | Client Doc No.:
|  |  | PRIMERO |  |  |  | FORTESCUE METALS GROUP LTD.
Name: (print)
Position Title
Signature
Date
INSPECTION AND TEST PLAN 02704-ITP-CI-001
INSPECTION AND TEST PLAN 02704-ITP-CI-001
INSPECTION AND TEST PLAN 02704-ITP-CI-001
EARTHWORKS
EARTHWORKS
EARTHWORKS

## ITP-002
CLIENT: |  | FMG Solomon |  |  |  |  | DOCUMENT |  | I.T.P. | Rev 0 |  | Page 1 of 4
PROJECT: |  | CLIENT REFERENCE No: |  |  |  |  | SCOPE OF ITP: |  | Concrete | Primero Job No: |  |  | 2704
|  | Prepared By: |  |  | Darren Duthie
|  | Final Release/Responsibility by: | [7 empty] | Primero Doc No.: |  |  | 02704-ITP-CI-002
|  | CLIENT APPROVAL | [7 empty] | Client Doc No.:
REF | INSPECTION AND TEST ACTIVITY |  |  | APPLICABLE DOCUMENT OR PROCEDURE ETC. |  | ACCEPTANCE CRITERIA | VERIFYING DOCUMENT |  |  | INSPECTION AND VERIFICATION
[10 empty] | Primero |  | Client |  | 3rd Party Inspection
[10 empty] | ACT. | SIG. | ACT. | SIG. | ACT. | SIG.
1 | Planning
1.1 | Quality Management Plan |  |  |  |  | Submitted & Approved |  |  |  | H |  | H
1.2 | Construction Drawings |  |  |  |  | AFC Drawings |  |  |  | H |  | H
1.3 | Safe Work Instructions |  |  |  |  | Submitted & Approved |  |  |  | R |  | R
1.4 | Approval of Concrete Mix Design |  |  | AFC Drawings |  | AS-1379 | NATA Test Results |  |  | R |  | H
Trial Mix
2 | Formwork Installation
2.1 | Confirm formwork is secured to |  |  | 100-SP-CI-0003 |  | AFC Drawings | ITR 203, ITR-204 |  |  |  |  | M
| correct lines and levels |  |  |  |  | Formwork Drawings |  |  |  | W
AS-3610
2.2 | Survey formwork to ensure within |  |  | 100-SP-CI-0003 |  | AFC Drawings | ITR 203, ITR-204 |  |  | W |  | M
| tolerance |  |  |  |  | AS-3610
2.3 | Inspect formwork to ensure |  |  | 100-SP-CI-0003 |  | Formwork Drawings | ITR 203, ITR-204 |  |  | W |  | M
| compliance to design |  |  |  |  | AFC Drawings
3 | Reinforcment Installation
3.1 | Reinforcement is processed, bent to |  |  | 100-SP-CI-0003 |  | AS-4671 | ISO 9001 |  |  | R |  | R
| specifications | [5 empty] | ACRS Certificates
Mill Certificates
3.2 | Reinforcement is bundled, tagged and stored to |  |  | 100-SP-CI-0003 |  | AS-4671 | Delivery Schedules |  |  | W,R |  | M
specifications
3.1 | Ensure all materials are clean, cut and bent to |  |  | 100-SP-CI-0003 |  | AFC Drawings | ITR 203, ITR-204 |  |  | M |  | M
| schedules |  |  |  |  | AS-4671
LEGEND |  | H = HOLD POINT |  |  | ACT = ACTIVITY |  |  | R/A = REVIEW & APPROVE DOC. |  |  |  | D = DIMENSIONAL INSPECTION
|  | S = SUBMIT DOCUMENT TO CLIENT |  |  | W = WITNESS POINT |  |  | V = VISUAL INSPECTION |  |  |  | V/S = VERIFYING SIGNATURE
|  | M = MONITOR ON A RANDOM BASIS |  |  | W @ R = WITNESS @ RANDOM |  |  | A = APPROVE |  |  |  | R & C = REVIEW & COMMENT
CLIENT: |  | FMG Solomon |  |  |  |  | DOCUMENT |  | I.T.P. | Rev 0 |  | Page 2 of 4
PROJECT: |  | CLIENT REFERENCE No: |  |  |  |  | SCOPE OF ITP: |  | Concrete | Primero Job No: |  |  | 2704
|  | Prepared By: |  |  | Darren Duthie
|  | Final Release/Responsibility by: | [7 empty] | Primero Doc No.: |  |  | 02704-ITP-CI-002
|  | CLIENT APPROVAL | [7 empty] | Client Doc No.:
REF | INSPECTION AND TEST ACTIVITY |  |  | APPLICABLE DOCUMENT OR PROCEDURE ETC. |  | ACCEPTANCE CRITERIA | VERIFYING DOCUMENT |  |  | INSPECTION AND VERIFICATION
[10 empty] | Primero |  | Client |  | 3rd Party Inspection
[10 empty] | ACT. | SIG. | ACT. | SIG. | ACT. | SIG.
3.2 | Confirm all reinforcement is in place and secured |  |  | 100-SP-CI-0003 |  | AFC Drawings | ITR 203, ITR-204 |  |  | W |  | M
3.3 | Check cover is in compliance to specifications |  |  | 100-SP-CI-0003 |  | AFC Drawings | ITR 203, ITR-204 |  |  | W |  | M
and drawings
3.4 | Ensure all supports, chairs, blocks are in place |  |  | 100-SP-CI-0003 |  | AFC Drawings | ITR 203, ITR-204 |  |  | W |  | M
3.5 | Verify splicing is as per drawings and |  |  | 100-SP-CI-0003 |  | AFC Drawings | ITR 203, ITR-204 |  |  | W |  | M
| specifications |  |  |  |  | AS-3600
3.6 | Check reinforcement is sufficiently fixed |  |  | 100-SP-CI-0003 |  | AFC Drawings | ITR 203, ITR-204 |  |  | W |  | M
4 | Embedments
4.1 | Embedments are to specifications, |  |  | 100-SP-CI-0003 |  | AFC Drawings | Vendor's ITP |  |  | W |  | W
| HD bolts, cast in angles, plates and | [5 empty] | Mill Certificates
| ferrules | [5 empty] | WPQ's, WP's
[6 empty] | AS-4100 | Galvanising reports
Material reports
ITR 203, ITR-204
4.2 | Lifting anchors and brace points |  |  | Approved engineered |  | AS-3850 | Manufacturer's report |  |  | W |  | W
|  |  |  | shop drawings |  | AS-3600 | Lifting engineered design
ITR-204
4.3 | Placement of embedment items are to |  |  | 100-SP-CI-0003 |  | AFC Drawings | ITR 203, ITR-204 |  |  | W |  | M
specifications and drawings
4.4 | Final visual inspection of all embedments |  |  | 100-SP-CI-0003 |  | AFC Drawings | ITR 203, ITR-204 |  |  | W |  | M
LEGEND |  | H = HOLD POINT |  |  | ACT = ACTIVITY |  |  | R/A = REVIEW & APPROVE DOC. |  |  |  | D = DIMENSIONAL INSPECTION
|  | S = SUBMIT DOCUMENT TO CLIENT |  |  | W = WITNESS POINT |  |  | V = VISUAL INSPECTION |  |  |  | V/S = VERIFYING SIGNATURE
|  | M = MONITOR ON A RANDOM BASIS |  |  | W @ R = WITNESS @ RANDOM |  |  | A = APPROVE |  |  |  | R & C = REVIEW & COMMENT
CLIENT: |  | FMG Solomon |  |  |  |  | DOCUMENT |  | I.T.P. | Rev 0 |  | Page 3 of 4
PROJECT: |  | CLIENT REFERENCE No: |  |  |  |  | SCOPE OF ITP: |  | Concrete | Primero Job No: |  |  | 2704
|  | Prepared By: |  |  | Darren Duthie
|  | Final Release/Responsibility by: | [7 empty] | Primero Doc No.: |  |  | 02704-ITP-CI-002
|  | CLIENT APPROVAL | [7 empty] | Client Doc No.:
REF | INSPECTION AND TEST ACTIVITY |  |  | APPLICABLE DOCUMENT OR PROCEDURE ETC. |  | ACCEPTANCE CRITERIA | VERIFYING DOCUMENT |  |  | INSPECTION AND VERIFICATION
[10 empty] | Primero |  | Client |  | 3rd Party Inspection
[10 empty] | ACT. | SIG. | ACT. | SIG. | ACT. | SIG.
4.5 | Final pre pour survey of embedment items |  |  | 100-SP-CI-0003 |  | Survey Report | ITR 203, ITR-204 |  |  | W |  | R
placement to ensure within tolerance
5 | Concrete Placement
5.1 | Signed off Concrete Pre Pour ITR's |  |  | 100-SP-CI-0003 |  | AFC Drawings | ITR 203, ITR-204 |  |  | H |  | H
5.2 | Correct Mix Code Delivered |  |  | 100-SP-CI-0003 |  | AFC Drawings | Batch Docket |  |  | W |  | M
Trial Mix
5.3 | Concrete Testing - Temperture, Slump Strength |  |  | 100-SP-CI-0003 |  | AS-1012 | Field Testing Sheet |  |  | W |  | R
[6 empty] | AS-1379 | NATA Test Results
5.4 | Concrete placement |  |  | 100-SP-CI-0003 |  | AS-3600 | ITR 203, ITR-204 |  |  | W |  | M
AFC Drawings
5.5 | Construction Joints |  |  | 100-SP-CI-0003 |  | AS-3600 | ITR-206 |  |  | W |  | M
AFC Drawings
5.6 | Compaction |  |  | 100-SP-CI-0003 |  |  | ITR 203, ITR-204 |  |  | W |  | M
5.7 | Curing |  |  | 100-SP-CI-0003 |  | AS-3799 | ITR 203, ITR-204 |  |  | W |  | M
Manufacturer's TDS
5.8 | Inspect concrete surfaces after formwork removal |  |  | 100-SP-CI-0003 |  | AS3600 | ITR-206 |  |  | W |  | R
5.9 | Concrete Repairs |  |  | 100-SP-CI-0003 |  | Approved Concrete | ITR-206 |  |  | W |  | W
Repair Methodology
6 | Inspection
6.1 | Survey and issue as built of completed structure |  |  | 100-SP-CI-0003 |  | AFC Drawings | Survey Reports |  |  | H |  | R
7 | Close Out Documentation
7.1 | Compile and submit all signed QA documentation |  |  | 100-SP-CI-0003 |  |  | MDR |  |  | R,S |  | R
LEGEND |  | H = HOLD POINT |  |  | ACT = ACTIVITY |  |  | R/A = REVIEW & APPROVE DOC. |  |  |  | D = DIMENSIONAL INSPECTION
|  | S = SUBMIT DOCUMENT TO CLIENT |  |  | W = WITNESS POINT |  |  | V = VISUAL INSPECTION |  |  |  | V/S = VERIFYING SIGNATURE
|  | M = MONITOR ON A RANDOM BASIS |  |  | W @ R = WITNESS @ RANDOM |  |  | A = APPROVE |  |  |  | R & C = REVIEW & COMMENT
CLIENT: |  | FMG Solomon |  |  |  |  | DOCUMENT |  | I.T.P. | Rev A |  | Page 4 of 4
PROJECT: |  | CLIENT REFERENCE No: |  |  |  |  | SCOPE OF ITP: |  | Earthworks | Primero Job No: |  |  | 2704
|  | Prepared By: |  |  | Darren Duthie
|  | Final Release/Responsibility by: | [7 empty] | Primero Doc No.: |  |  | 02704-ITP-CI-001
|  | CLIENT APPROVAL | [7 empty] | Client Doc No.:
|  |  | PRIMERO |  |  |  | FORTESCUE METALS GROUP LTD.
Name: (print)
Position Title
Signature
Date
INSPECTION AND TEST PLAN 02704-ITP-CI-001
INSPECTION AND TEST PLAN 02704-ITP-CI-002
INSPECTION AND TEST PLAN 02704-ITP-CI-002
INSPECTION AND TEST PLAN 02704-ITP-CI-002
INSPECTION AND TEST PLAN 02704-ITP-CI-001
CIVIL
CIVIL
CIVIL