## Sheet1
ITP Discipline |  | Mechanical Equipment Installation |  | Project Area | Yamarna Gas Pipeline & Stations
Project Title |  | Design and Supply of Yamarna Gas Skids |  | Revision | B
Primero Document No. |  | 06702-ITP-ME-001 |  | Date | 2017-12-05
Client |  | APA Operations Pty Ltd |  | Prepared | R. O’Callaghan
Client Document No. |  | YGP-020-ITP-QM-0004 |  | Approved | B. Zlnay
H = HOLD POINT |  | V = VISUAL INSPECTION | R = REVIEW | D = DIMENSIONAL INSPECTION |  | WR = WITNESS @ RANDOM
W = WITNESS POINT |  | M = MONITOR ON A RANDOM BASIS | A = APPROVE | S = SUBMIT DOCUMENT TO CLIENT
REF | INSPECTION AND TEST ACTIVITY | APPLICABLE DOCUMENT OR PROCEDURE ETC. | ACCEPTANCE CRITERIA | VERIFYING DOCUMENT | INSPECTION AND VERIFICATION
[5 empty] | Primero |  | Client |  | 3RD Party Inspection
[5 empty] | Activity | Signature | Activity | Signature | Activity | Signature
1 | SPECIFICATIONS
1.1 | Review Scope of Work | YGP-SOW-A-0001 | Not Applicable | Contract Document | R |  | R
1.2 | Review Design | Packaged Equipment Specification, YGP-SP-A-0002 | YGP-SOW-A-0001 | Design Approval, VDS | S |  | R
1.3 | Review Drawings | AFC Drawings | Drawings | AFC Drawings | S |  | R
2 | EQUIPMENT
2.1 | Inspect Vendor Mechanical Equipment | YGP-SP-A-0002 Vendor Documentation | Compliance for Manufacture | Vendor MDR / Documentation | W |  | WR / R
3 | PREPARE FOR INSTALLATION
3.1 | Dimensional check of structural steelwork prior to installation | Structural Steel Erection 530-SP-S-0004 | Vendor Documents and Structural Drawings | General Arrangement Drawings | V |  | R
3.2 | Review Previous Documentation of tension inspection of Bolts on Structural Steel work | Structural Steel Erection 530-SP-S-0004 | 530-SP-S-0004 | Bolt Torque Record 06702-ITR-ST-101 | R |  | R
4 | INSTALL MECHANICAL EQUIPMENT
4.1 | Install equipment onto new structural steelwork | Vendor supplied documents and drawings | Vendor Specification and drawings | Inspection and Test Records | M |  | R
4.2 | Confirm Elevations and Centre lines of Mechanical Equipment | Packaged Equipment Specification, YGP-SP-A-0002 | YGP-SP-A-0002, Vendor Documents | As-built Drawings | H |  | W
4.3 | Carry out tension inspection of hold down bolts | Structural Steel Erection 530-SP-S-0004 | Vendor Documents | Bolt Torque Record 06702-ITR-ST-101 | S |  | R
4.4 | Bolt up piping and instrumentation | Piping ITP-PP-001 | 530-SP-P-0002, Vendor Documents | Alignment Report (where applicable), 06702-ITR-PP-101 | S |  | R
4.5 | Preservation | Packaged Equipment Specification, YGP-SP-A-0002 | YGP-SP-A-0002, Vendor Documents | 06702-ITR-ME-103 | H |  | W
4.6 | Pre-commissioning (as applicable) | Commissioning test plan | Commissioning test plan | Commissioning Test Report | H |  | H
5 | PREPARATION FOR HANDOVER
5.1 | Touch up painting | Coating Subcontractor Procedure, Coating Subcontractor ITP | 530-SP-M-9602 | Coatings Inspection Report (where required) | M |  | R
5.2 | Prepare all documentation for handover and sign off | Contract Document | YGP-SOW-A-0001 | All check sheets referenced, ITP to be signed off, As Built Drawings completed. | S |  | A
3 | VERIFICATION
3.1 | Punchlisting | AFC Drawings, YGP-SOW-A-0001 | AFC Drawings, YGP-SOW-A-0001 | Completed Client Punchlist | H |  | H