## Register
INSPECTION AND TEST PLAN (ITP) REGISTER
|  | CLIENT : | Rio Tinto
|  | PROJECT : | Fuel Management and Monitoring System
|  | PROJECT No : | 1709
SITE :
|  | LAST UPDATED : | 2014-08-28
ITR No. | Title |  |  | Originator | Date Issued | Date Completed
ITP-001 | SITE INSTALLATION - Marandoo |  |  | Gavin Satie | XX/XX/XXXX | XX/XX/XXXX
ITP-002 | ELECTRICAL AND INSTRUMENTATION INSTALLATION - Brockman 2 |  |  | Gavin Satie | XX/XX/XXXX | XX/XX/XXXX
ITP-003 | ELECTRICAL AND INSTRUMENTATION INSTALLATION - Brockman 4 |  |  | Gavin Satie | XX/XX/XXXX | XX/XX/XXXX
ITP-004 | ELECTRICAL AND INSTRUMENTATION INSTALLATION - Nammulidi |  |  | Gavin Satie | XX/XX/XXXX | XX/XX/XXXX

## ITP-001 Marandoo
ITP Number: |  | 01709-006-ITP-QA-001 | Client Contract Number: | PE350080/J/CC/1000 FMMS | Contract Item Number: |  | Legend: | W = Witness | S = Subcontractor |  | I = In House
Revision Number: |  | A | Contractor Approval: |  | Equipment Number: |  |  | H = Hold | SV = Surveillance |  | R = Review
Contractor: |  | Primero Group | Description of Service: | Installation of the Fuel Management and Monitoring System
Works Locations: |  | Marandoo
Task Number | Probable Date | Task Description | Location Code (I or S) | Controlling Procedure or Instruction | Acceptance Criteria | Verifying Documents | Inspection Requirements |  |  |  |  | Contractor Signature
[7 empty] | Contractor | Engineer |  |  | Client
[8 empty] | Insp | Engineer | Signature
1 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
DESIGN/SPECIFICATIONS
|  | Review Drawings & Data Sheets | I | AFC Drawings & Data Sheets | Austrialian Standards Client Specifications and Standards Engineering Data | AFC Drawings, VDDI | W
APPROVALS
|  | Submit Project Documentation, ITP, | I | ITP | Austrialian Standards Client Specifications and Standards Engineering Data | Approved ITP’s | W, H
MATERIALS
|  | Inspect materials a per Material Control Procedure 01709-PRO-PM-017 | I | AFC Drawings, Material Control Procedure, and Client Specifications, refer Note 1 | Austrialian Standards Client Specifications and Standards Engineering Data | Delivery Dockets, Material Register & Certificates, Consumable Certificates, Data Sheets | H
|  | Store materials to eliminate damage | I | Material Control Procedure | Austrialian Standards Client Specifications and Standards Engineering Data |  | SV
|  | Check supply of vendor equipment for completeness | I | SOW | Visual Inspection | Vendor Supply List & Delivery Docket | W
SITE ESTABLISHMENT
|  | Site Preparation, Planning and Inspection | I | 01709-SWI-HS-093 Site Preparation, Planning and Inspection | 01709-SWI-HS-093 Site Preparation, Planning and Inspection Electrical Test and Tag Register Rigging Register | N/A | SV
FACTORY ACCEPTANCE TESTING
|  | Verification of the FMMS System | I | Factory Acceptance Plan | Austrialian Standards Client Specifications and Standards Engineering Data | Signed off FAT Plan Punchlist items cleared | H
ELECTRICAL AND INSTRUMENT INSTALLATION
|  | Installation of Cable Ladders and Trays | I | 01709-PRO-EL-005 Inspection Test Record Procedure 01709-SWI-HS-091 Installation of Cable Tray and Cable Ladder 01709-PRO-EL-004_A Electrical ITR Matrix Procedure | Austrialian Standards Client Specifications and Standards Engineering Data | 01709-ITR-EL-033 Cable Tray - Ladder | R
|  | Installation of Below Ground Conduits | I | 01709-PRO-EL-005 Inspection Test Record Procedure 01709-SWI-HS-094 Trenching, Excavating, Pot Holing 01709-PRO-EL-004_A Electrical ITR Matrix Procedure | Austrialian Standards Client Specifications and Standards Engineering Data | 01709-ITR-EL-036 Underground Cable Installation | W, R
|  | Installation of Aboveground Rigid Discontinuous Conduit | I | 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure | Austrialian Standards Client Specifications and Standards Engineering Data | 01709-ITR-EL-034 Above Ground Conduit | R
|  | Installation of Cables and Fibre Optic Cables | I | 01709-PRO-EL-005 Inspection Test Record Procedure 01709-SWI-HS-092 Installation of Cables 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure | Austrialian Standards Client Specifications and Standards Engineering Data | 01709-ITR-EL-049 Cable Installation Tesing and Termination 01709-ITR-EL-036 Underground Cable Installation | W, R
|  | Installation of Electrical Earthing | I | 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure | Austrialian Standards Client Specifications and Standards Engineering Data | 01709-ITR-EL-015 Electrical Earthing | W, R
|  | Testing and Termination Cables | I | 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure | Austrialian Standards Client Specifications and Standards Engineering Data | 01709-ITR-EL-049 Cable Installation Tesing and Termination | R
|  | Installation of Control Panels | I | 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure | Austrialian Standards Client Specifications and Standards Engineering Data | 01709-ITR-EL-023 Control Panel | R
|  | Installation of Steel Erection/Control Panel Frame | I | Construction Methodology (Schedule M of the Contract) | Austrialian Standards Client Specifications and Standards Engineering Data | 01709-ITR-ME-016 01709-ITR-ME-015 01709-ITR-ME-014 | R
|  | Inpection of Equipment Pre Installation | I | 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure | Austrialian Standards Client Specifications and Standards Engineering Data | 01709-ITR-IN-003 Equipment Pre-Installation Verification | R
|  | Installation of Instruments | I | 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure | Austrialian Standards Client Specifications and Standards Engineering Data | 01709-ITR-IN-001 Instrument Installation 01709-ITR-IN-003 Equipment Pre-Installation Verification | R
|  | Instrument Loop Checks | I | 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure | 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure | 01709-ITR-IN-007 Instrument Loop Check | R
|  | CONCRETE PRECAST INSTALLATION | I
|  | Earthworks methods and compaction information received and verified against design | I | Contractors Construction Methodology (Schedule M of the Contract) | Austrialian Standards Client Specifications and Standards Engineering Data | Visual Inspection | R
|  | Excavated levels checked against design | I | Contractors Construction Methodology (Schedule M of the Contract) | Austrialian Standards Client Specifications and Standards Engineering Data | Visual Inspection | W, R
|  | Bedding sand or fines added where required, thickness not to exceed 50mm | I | Construction Methodology (Schedule M of the Contract) | Austrialian Standards Client Specifications and Standards Engineering Data | Visual Inspection | R
|  | Inspect Pre-cast footings for defects and tolerances |  | Construction Methodology (Schedule M of the Contract) | Austrialian Standards Client Specifications and Standards Engineering Data | Visual Inspection | R
|  | Pre-cast footings landed and postion confirmed | I | Construction Methodology (Schedule M of the Contract) | Austrialian Standards Client Specifications and Standards Engineering Data | Visual Inspection | R
MECHANICAL INSTALLATION
|  | Removal of all old Hatch Lid | I | Construction Methodology (Schedule M of the Contract) | Austrialian Standards Client Specifications and Standards Engineering Data | Visual Inspection | R
|  | Installation of new hatch lid for tank - Ensure all surfaces a clean - Correct gasket is used - Correct Bolts are used - Bolts Torqued to the correct settings | I | Construction Methodology (Schedule M of the Contract) | Austrialian Standards Client Specifications and Standards Engineering Data | Visual Inspection 01709-ITR-ME-015 Bolt Tensioning Record | R
NOTICE OF ENERGISATION
|  | Energisation of FMMS System | I | 00000-PRO-CM-001 Notice of Energisation Procedure Client Specifications | Austrialian Standards Client Specifications and Standards Engineering Data As Built Drawings Completed ITR's Permits | Application Notice of Energisation | H
COMMISSIONING
|  | Commissioning of FMMS System | I | Commissioning Test Procedure | Austrialian Standards Client Specifications and Standards Engineering Data As Built Drawings Completed ITR's Notice of Energisation | Signed off Commissioning Procedure Punchlist | H
FINAL INSPECTION ON COMPLETION
|  | -Carry out final inspection -Generate punch list -Verification / clearance of punch list | I | 01709-PLN-PM-002, Client Specifications, | Austrialian Standards Client Specifications and Standards Engineering Data | Field Inspection Checklist (FIC) 's Completions database | H
FINALISE DOCUMENTATION
|  | Progressively check all test reports are correct. | I | 01709-PLN-PM-002, Client Specifications | Austrialian Standards Client Specifications and Standards Engineering Data | Reviewed and Approved ITR's | H
|  | Sign off Inspection & Test Plan. | I | 01709-PLN-PM-002, Client Specifications | Austrialian Standards Client Specifications and Standards Engineering Data | ITP | R
|  | MDR to be progressively compiled and submitted to client for final approval. | I | 01709-PLN-PM-002, Client Specifications | Austrialian Standards Client Specifications and Standards Engineering Data | MDR | R

## ITP-002 Nammuldi
ITP Number: |  | 01709-005-ITP-QA-002 | Client Contract Number: | PE350080/J/CC/1000 FMMS | Contract Item Number: |  | Legend: | W = Witness | S = Subcontractor |  | I = In House
Revision Number: |  | A | Contractor Approval: |  | Equipment Number: |  |  | H = Hold | SV = Surveillance |  | R = Review
Contractor: |  | Primero Group | Description of Service: | Installation of the Fuel Management and Monitoring System
Works Locations: |  | Nammuldi - Main Fuel Farm
Task Number | Probable Date | Task Description | Location Code (I or S) | Controlling Procedure or Instruction | Acceptance Criteria | Verifying Documents | Inspection Requirements |  |  |  |  | Contractor Signature
[7 empty] | Contractor | Engineer |  |  | Client
[8 empty] | Insp | Engineer | Signature
1 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
DESIGN/SPECIFICATIONS
1 |  | 2: Review Drawings & Data Sheets; 3: I; 4: AFC Drawings & Data Sheets; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: AFC Drawings, VDDI; 7: W
APPROVALS
2 |  | 2: Submit Project Documentation, ITP,; 3: I; 4: ITP; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Approved ITP’s; 7: W, H
MATERIALS
3 |  | 2: Inspect materials a per Material Control Procedure 01709-PRO-PM-017; 3: I; 4: AFC Drawings, Material Control Procedure, and Client Specifications, refer Note 1; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Delivery Dockets, Material Register & Certificates, Consumable Certificates, Data Sheets; 7: H
4 |  | 2: Store materials to eliminate damage; 3: I; 4: Material Control Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 7: SV
5 |  | 2: Check supply of vendor equipment for completeness; 3: I; 4: SOW; 5: Visual Inspection; 6: Vendor Supply List & Delivery Docket; 7: W
SITE ESTABLISHMENT
6 |  | 2: Site Preparation, Planning and Inspection; 3: I; 4: 01709-SWI-HS-093 Site Preparation, Planning and Inspection; 5: 01709-SWI-HS-093 Site Preparation, Planning and Inspection Electrical Test and Tag Register Rigging Register; 6: N/A; 7: SV
FACTORY ACCEPTANCE TESTING
7 |  | 2: Verification of the FMMS System; 3: I; 4: Factory Acceptance Plan; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Signed off FAT Plan Punchlist items cleared; 7: H
ELECTRICAL AND INSTRUMENT INSTALLATION
8 |  | 2: Installation of Cable Ladders and Trays; 3: I; 4: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-SWI-HS-091 Installation of Cable Tray and Cable Ladder 01709-PRO-EL-004_A Electrical ITR Matrix Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: 01709-ITR-EL-033 Cable Tray - Ladder; 7: R
9 |  | 2: Installation of Aboveground Rigid Discontinuous Conduit; 3: I; 4: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: 01709-ITR-EL-034 Above Ground Conduit; 7: R
10 |  | 2: Installation of Cables; 3: I; 4: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-SWI-HS-092 Installation of Cables 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: 01709-ITR-EL-049 Cable Installation Tesing and Termination; 7: W, R
11 |  | 2: Installation of Electrical Earthing; 3: I; 4: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: 01709-ITR-EL-015 Electrical Earthing; 7: W, R
12 |  | 2: Testing and Termination Cables; 3: I; 4: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: 01709-ITR-EL-049 Cable Installation Tesing and Termination; 7: R
13 |  | 2: Installation of Control Panels; 3: I; 4: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: 01709-ITR-EL-023 Control Panel; 7: R
14 |  | 2: Installation of Steel Erection/Control Panel Frame; 3: I; 4: Construction Methodology (Schedule M of the Contract); 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: 01709-ITR-ME-016 01709-ITR-ME-015 01709-ITR-ME-014; 7: R
15 |  | 2: Inpection of Equipment Pre Installation; 3: I; 4: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: 01709-ITR-IN-003 Equipment Pre-Installation Verification; 7: R
16 |  | 2: Installation of Instruments; 3: I; 4: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: 01709-ITR-IN-001 Instrument Installation 01709-ITR-IN-003 Equipment Pre-Installation Verification; 7: R
17 |  | 2: Instrument Loop Checks; 3: I; 4: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure; 5: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure; 6: 01709-ITR-IN-007 Instrument Loop Check; 7: R
|  | CONCRETE PRECAST INSTALLATION | I
18 |  | 2: Earthworks methods and compaction information received and verified against design; 3: I; 4: Contractors Construction Methodology (Schedule M of the Contract); 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Visual Inspection; 7: R
19 |  | 2: Excavated levels checked against design; 3: I; 4: Contractors Construction Methodology (Schedule M of the Contract); 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Visual Inspection; 7: W, R
20 |  | 2: Bedding sand or fines added where required, thickness not to exceed 50mm; 3: I; 4: Construction Methodology (Schedule M of the Contract); 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Visual Inspection; 7: R
21 |  | 2: Inspect Pre-cast footings for defects and tolerances; 3: I; 4: Construction Methodology (Schedule M of the Contract); 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Visual Inspection; 7: R
22 |  | 2: Pre-cast footings landed and postion confirmed; 3: I; 4: Construction Methodology (Schedule M of the Contract); 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Visual Inspection; 7: R
NOTICE OF ENERGISATION
23 |  | 2: Energisation of FMMS System; 3: I; 4: 00000-PRO-CM-001 Notice of Energisation Procedure Client Specifications; 5: Austrialian Standards Client Specifications and Standards Engineering Data As Built Drawings Completed ITR's Permits; 6: Application Notice of Energisation; 7: H
COMMISSIONING
24 |  | 2: Commissioning of FMMS System; 3: I; 4: Commissioning Test Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data As Built Drawings Completed ITR's Notice of Energisation; 6: Signed off Commissioning Procedure Punchlist; 7: H
FINAL INSPECTION ON COMPLETION
25 |  | 2: Carry out final inspection Generate punchlist; 3: I; 4: 01709-PLN-PM-002, Client Specifications,; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Field Inspection Checklist (FIC) 's Completions database; 7: H
26 |  | 2: Verification / clearance of punchlist; 3: I; 4: 01709-PLN-PM-002, Client Specifications,; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Field Inspection Checklist (FIC) 's Completions database
FINALISE DOCUMENTATION
27 |  | 2: Progressively check all test reports are correct.; 3: I; 4: 01709-PLN-PM-002, Client Specifications; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Reviewed and Approved ITR's; 7: H
28 |  | 2: Sign off Inspection & Test Plan.; 3: I; 4: 01709-PLN-PM-002, Client Specifications; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: ITP; 7: R
29 |  | 2: MDR to be progressively compiled and submitted to client for final approval.; 3: I; 4: 01709-PLN-PM-002, Client Specifications; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: MDR; 7: R

## ITP-002 Brockman 2
ITP Number: |  | 01709-004-ITP-QA-002 | Client Contract Number: | PE350080/J/CC/1000 FMMS | Contract Item Number: |  | Legend: | W = Witness | S = Subcontractor |  | I = In House
Revision Number: |  | A | Contractor Approval: |  | Equipment Number: |  |  | H = Hold | SV = Surveillance |  | R = Review
Contractor: |  | Primero Group | Description of Service: | Installation of the Fuel Management and Monitoring System
Works Locations: |  | Brockman 2 - Main Fuel Farm
Task Number | Probable Date | Task Description | Location Code (I or S) | Controlling Procedure or Instruction | Acceptance Criteria | Verifying Documents | Inspection Requirements |  |  |  |  | Contractor Signature
[7 empty] | Contractor | Engineer |  |  | Client
[8 empty] | Insp | Engineer | Signature
1 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
DESIGN/SPECIFICATIONS
1 |  | 2: Review Drawings & Data Sheets; 3: I; 4: AFC Drawings & Data Sheets; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: AFC Drawings, VDDI; 7: W
APPROVALS
2 |  | 2: Submit Project Documentation, ITP,; 3: I; 4: ITP; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Approved ITP’s; 7: W, H
MATERIALS
3 |  | 2: Inspect materials a per Material Control Procedure 01709-PRO-PM-017; 3: I; 4: AFC Drawings, Material Control Procedure, and Client Specifications, refer Note 1; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Delivery Dockets, Material Register & Certificates, Consumable Certificates, Data Sheets; 7: H
4 |  | 2: Store materials to eliminate damage; 3: I; 4: Material Control Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 7: SV
5 |  | 2: Check supply of vendor equipment for completeness; 3: I; 4: SOW; 5: Visual Inspection; 6: Vendor Supply List & Delivery Docket; 7: W
SITE ESTABLISHMENT
6 |  | 2: Site Preparation, Planning and Inspection; 3: I; 4: 01709-SWI-HS-093 Site Preparation, Planning and Inspection; 5: 01709-SWI-HS-093 Site Preparation, Planning and Inspection Electrical Test and Tag Register Rigging Register; 6: N/A; 7: SV
FACTORY ACCEPTANCE TESTING
7 |  | 2: Verification of the FMMS System; 3: I; 4: Factory Acceptance Plan; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Signed off FAT Plan Punchlist items cleared; 7: H
ELECTRICAL AND INSTRUMENT INSTALLATION
8 |  | 2: Installation of Cable Ladders and Trays; 3: I; 4: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-SWI-HS-091 Installation of Cable Tray and Cable Ladder 01709-PRO-EL-004_A Electrical ITR Matrix Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: 01709-ITR-EL-033 Cable Tray - Ladder; 7: R
9 |  | 2: Installation of Aboveground Rigid Discontinuous Conduit; 3: I; 4: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: 01709-ITR-EL-034 Above Ground Conduit; 7: R
10 |  | 2: Installation of Cables; 3: I; 4: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-SWI-HS-092 Installation of Cables 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: 01709-ITR-EL-049 Cable Installation Tesing and Termination; 7: W, R
11 |  | 2: Installation of Electrical Earthing; 3: I; 4: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: 01709-ITR-EL-015 Electrical Earthing; 7: W, R
12 |  | 2: Testing and Termination Cables; 3: I; 4: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: 01709-ITR-EL-049 Cable Installation Tesing and Termination; 7: R
13 |  | 2: Installation of Control Panels; 3: I; 4: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: 01709-ITR-EL-023 Control Panel; 7: R
14 |  | 2: Installation of Steel Erection/Control Panel Frame; 3: I; 4: Construction Methodology (Schedule M of the Contract); 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: 01709-ITR-ME-016 01709-ITR-ME-015 01709-ITR-ME-014; 7: R
15 |  | 2: Inpection of Equipment Pre Installation; 3: I; 4: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: 01709-ITR-IN-003 Equipment Pre-Installation Verification; 7: R
16 |  | 2: Installation of Instruments; 3: I; 4: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: 01709-ITR-IN-001 Instrument Installation 01709-ITR-IN-003 Equipment Pre-Installation Verification; 7: R
17 |  | 2: Instrument Loop Checks; 3: I; 4: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure; 5: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure; 6: 01709-ITR-IN-007 Instrument Loop Check; 7: R
|  | CONCRETE PRECAST INSTALLATION | I
18 |  | 2: Earthworks methods and compaction information received and verified against design; 3: I; 4: Contractors Construction Methodology (Schedule M of the Contract); 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Visual Inspection; 7: R
19 |  | 2: Excavated levels checked against design; 3: I; 4: Contractors Construction Methodology (Schedule M of the Contract); 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Visual Inspection; 7: W, R
20 |  | 2: Bedding sand or fines added where required, thickness not to exceed 50mm; 3: I; 4: Construction Methodology (Schedule M of the Contract); 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Visual Inspection; 7: R
21 |  | 2: Inspect Pre-cast footings for defects and tolerances; 3: I; 4: Construction Methodology (Schedule M of the Contract); 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Visual Inspection; 7: R
22 |  | 2: Pre-cast footings landed and postion confirmed; 3: I; 4: Construction Methodology (Schedule M of the Contract); 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Visual Inspection; 7: R
NOTICE OF ENERGISATION
23 |  | 2: Energisation of FMMS System; 3: I; 4: 00000-PRO-CM-001 Notice of Energisation Procedure Client Specifications; 5: Austrialian Standards Client Specifications and Standards Engineering Data As Built Drawings Completed ITR's Permits; 6: Application Notice of Energisation; 7: H
COMMISSIONING
24 |  | 2: Commissioning of FMMS System; 3: I; 4: Commissioning Test Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data As Built Drawings Completed ITR's Notice of Energisation; 6: Signed off Commissioning Procedure Punchlist; 7: H
FINAL INSPECTION ON COMPLETION
25 |  | 2: Carry out final inspection Generate punchlist; 3: I; 4: 01709-PLN-PM-002, Client Specifications,; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Field Inspection Checklist (FIC) 's Completions database; 7: H
26 |  | 2: Verification / clearance of punchlist; 3: I; 4: 01709-PLN-PM-002, Client Specifications,; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Field Inspection Checklist (FIC) 's Completions database
FINALISE DOCUMENTATION
27 |  | 2: Progressively check all test reports are correct.; 3: I; 4: 01709-PLN-PM-002, Client Specifications; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Reviewed and Approved ITR's; 7: H
28 |  | 2: Sign off Inspection & Test Plan.; 3: I; 4: 01709-PLN-PM-002, Client Specifications; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: ITP; 7: R
29 |  | 2: MDR to be progressively compiled and submitted to client for final approval.; 3: I; 4: 01709-PLN-PM-002, Client Specifications; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: MDR; 7: R

## ITP-002 Brockman 4
ITP Number: |  | 01709-003-ITP-QA-002 | Client Contract Number: | PE350080/J/CC/1000 FMMS | Contract Item Number: |  | Legend: | W = Witness | S = Subcontractor |  | I = In House
Revision Number: |  | A | Contractor Approval: |  | Equipment Number: |  |  | H = Hold | SV = Surveillance |  | R = Review
Contractor: |  | Primero Group | Description of Service: | Installation of the Fuel Management and Monitoring System
Works Locations: |  | Brockman 4 - Main Fuel Farm
Task Number | Probable Date | Task Description | Location Code (I or S) | Controlling Procedure or Instruction | Acceptance Criteria | Verifying Documents | Inspection Requirements |  |  |  |  | Contractor Signature
[7 empty] | Contractor | Engineer |  |  | Client
[8 empty] | Insp | Engineer | Signature
1 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
DESIGN/SPECIFICATIONS
1 |  | 2: Review Drawings & Data Sheets; 3: I; 4: AFC Drawings & Data Sheets; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: AFC Drawings, VDDI; 7: W
APPROVALS
2 |  | 2: Submit Project Documentation, ITP,; 3: I; 4: ITP; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Approved ITP’s; 7: W, H
MATERIALS
3 |  | 2: Inspect materials a per Material Control Procedure 01709-PRO-PM-017; 3: I; 4: AFC Drawings, Material Control Procedure, and Client Specifications, refer Note 1; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Delivery Dockets, Material Register & Certificates, Consumable Certificates, Data Sheets; 7: H
4 |  | 2: Store materials to eliminate damage; 3: I; 4: Material Control Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 7: SV
5 |  | 2: Check supply of vendor equipment for completeness; 3: I; 4: SOW; 5: Visual Inspection; 6: Vendor Supply List & Delivery Docket; 7: W
SITE ESTABLISHMENT
6 |  | 2: Site Preparation, Planning and Inspection; 3: I; 4: 01709-SWI-HS-093 Site Preparation, Planning and Inspection; 5: 01709-SWI-HS-093 Site Preparation, Planning and Inspection Electrical Test and Tag Register Rigging Register; 6: N/A; 7: SV
FACTORY ACCEPTANCE TESTING
7 |  | 2: Verification of the FMMS System; 3: I; 4: Factory Acceptance Plan; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Signed off FAT Plan Punchlist items cleared; 7: H
ELECTRICAL AND INSTRUMENT INSTALLATION
8 |  | 2: Installation of Cable Ladders and Trays; 3: I; 4: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-SWI-HS-091 Installation of Cable Tray and Cable Ladder 01709-PRO-EL-004_A Electrical ITR Matrix Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: 01709-ITR-EL-033 Cable Tray - Ladder; 7: R
9 |  | 2: Installation of Aboveground Rigid Discontinuous Conduit; 3: I; 4: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: 01709-ITR-EL-034 Above Ground Conduit; 7: R
10 |  | 2: Installation of Cables; 3: I; 4: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-SWI-HS-092 Installation of Cables 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: 01709-ITR-EL-049 Cable Installation Tesing and Termination; 7: W, R
11 |  | 2: Installation of Electrical Earthing; 3: I; 4: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: 01709-ITR-EL-015 Electrical Earthing; 7: W, R
12 |  | 2: Testing and Termination Cables; 3: I; 4: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: 01709-ITR-EL-049 Cable Installation Tesing and Termination; 7: R
13 |  | 2: Installation of Control Panels; 3: I; 4: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: 01709-ITR-EL-023 Control Panel; 7: R
14 |  | 2: Installation of Steel Erection/Control Panel Frame; 3: I; 4: Construction Methodology (Schedule M of the Contract); 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: 01709-ITR-ME-016 01709-ITR-ME-015 01709-ITR-ME-014; 7: R
15 |  | 2: Inpection of Equipment Pre Installation; 3: I; 4: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: 01709-ITR-IN-003 Equipment Pre-Installation Verification; 7: R
16 |  | 2: Installation of Instruments; 3: I; 4: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: 01709-ITR-IN-001 Instrument Installation 01709-ITR-IN-003 Equipment Pre-Installation Verification; 7: R
17 |  | 2: Instrument Loop Checks; 3: I; 4: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure; 5: 01709-PRO-EL-005 Inspection Test Record Procedure 01709-PRO-EL-004_A Electrical ITR Matrix Procedure 01709-PRO-EL-002_A Electrical Testing and Reporting Procedure 01709-PRO-EL-007 Calibration and Equipment Procedure; 6: 01709-ITR-IN-007 Instrument Loop Check; 7: R
|  | CONCRETE PRECAST INSTALLATION | I
18 |  | 2: Earthworks methods and compaction information received and verified against design; 3: I; 4: Contractors Construction Methodology (Schedule M of the Contract); 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Visual Inspection; 7: R
19 |  | 2: Excavated levels checked against design; 3: I; 4: Contractors Construction Methodology (Schedule M of the Contract); 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Visual Inspection; 7: W, R
20 |  | 2: Bedding sand or fines added where required, thickness not to exceed 50mm; 3: I; 4: Construction Methodology (Schedule M of the Contract); 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Visual Inspection; 7: R
21 |  | 2: Inspect Pre-cast footings for defects and tolerances; 3: I; 4: Construction Methodology (Schedule M of the Contract); 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Visual Inspection; 7: R
22 |  | 2: Pre-cast footings landed and postion confirmed; 3: I; 4: Construction Methodology (Schedule M of the Contract); 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Visual Inspection; 7: R
NOTICE OF ENERGISATION
23 |  | 2: Energisation of FMMS System; 3: I; 4: 00000-PRO-CM-001 Notice of Energisation Procedure Client Specifications; 5: Austrialian Standards Client Specifications and Standards Engineering Data As Built Drawings Completed ITR's Permits; 6: Application Notice of Energisation; 7: H
COMMISSIONING
24 |  | 2: Commissioning of FMMS System; 3: I; 4: Commissioning Test Procedure; 5: Austrialian Standards Client Specifications and Standards Engineering Data As Built Drawings Completed ITR's Notice of Energisation; 6: Signed off Commissioning Procedure Punchlist; 7: H
FINAL INSPECTION ON COMPLETION
25 |  | 2: Carry out final inspection Generate punchlist; 3: I; 4: 01709-PLN-PM-002, Client Specifications,; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Field Inspection Checklist (FIC) 's Completions database; 7: H
26 |  | 2: Verification / clearance of punchlist; 3: I; 4: 01709-PLN-PM-002, Client Specifications,; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Field Inspection Checklist (FIC) 's Completions database
FINALISE DOCUMENTATION
27 |  | 2: Progressively check all test reports are correct.; 3: I; 4: 01709-PLN-PM-002, Client Specifications; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: Reviewed and Approved ITR's; 7: H
28 |  | 2: Sign off Inspection & Test Plan.; 3: I; 4: 01709-PLN-PM-002, Client Specifications; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: ITP; 7: R
29 |  | 2: MDR to be progressively compiled and submitted to client for final approval.; 3: I; 4: 01709-PLN-PM-002, Client Specifications; 5: Austrialian Standards Client Specifications and Standards Engineering Data; 6: MDR; 7: R