## Sheet1
ITP Discipline |  | Pressure Vessel Fabrication |  | Project Area | Yamarna Gas Pipeline & Stations
Project Title |  | Design and Supply of Yamarna Gas Skids |  | Revision | 0
Primero Document No. |  | 06702-MP002-ITP-QM-001 |  | Date | 2018-03-01
Client |  | APA Operations Pty Ltd |  | Prepared | R. O’Callaghan
Client Document No. |  | YGP-020-ITP-QM-0008 |  | Approved | B. Zlnay
H = HOLD POINT |  | V = VISUAL INSPECTION | R = REVIEW | D = DIMENSIONAL INSPECTION |  | WR = WITNESS @ RANDOM
W = WITNESS POINT |  | M = MONITOR ON A RANDOM BASIS | A = APPROVE | S = SUBMIT DOCUMENT TO CLIENT
REF | INSPECTION AND TEST ACTIVITY | APPLICABLE DOCUMENT OR PROCEDURE ETC. | ACCEPTANCE CRITERIA | VERIFYING DOCUMENT | INSPECTION AND VERIFICATION
[5 empty] | Fabricator |  | Primero |  | Client
[5 empty] | Activity | Signature | Activity | Signature | Activity | Signature
1 | SPECIFICATIONS
1.1 | Review Contract Documents & Verify Scope Of Work | Review Work Scope | 530-SP-M-0507 530-SP-M-9602 530-SP-A-0002 | 06702-MP002-ITP-QM-001 | R A |  | R A
| Mechanical Design & Detailed Drafting | Ensure Designer Has Correct Specification | AS 1210 AS 3992 530-SP-M-0507 | 06702-MP002-ITP-QM-001 | R |  | R |  | R A
| Submit Design Calculations & Drawings for Review | Check Design Calculations And Drawings | AS 1210, AS 1100 530-SP-A-0003 | Approved Calcs & Drawings | R A |  | R A |  | R A
| Submit Documents, Procedures Required From Supplier Document Schedule | Check Procedures With Contract Documents, Drawings & Specifications | 530-SP-A-0003 | Document Transmittal | R |  | R |  | R A
| Preparation of Welding Procedures & Welder Qualification. Submit For Approval | Verify Welding Codes And Standards | AS3992 530-SP-M-0507 | Approved WPS's & WQR's | R.A. |  | R.A. |  | R A W
| Third Party Verification Of Design Calculations And Drawings | Verify Design Calculations And Drawings | AS 1210, AS 1100, AS3920.1 | Design Verification Certificate | R |  | R |  | R A
MATERIALS CONTROL
| Procure Required Materials And Consumables | Verify Materials With Spec And Drawings | 530-SP-M-0507 | Purchase Order | SU |  | SU |  | SU
| Check materials for compliance with delivery docket, drawings, & required material certification | Check Material Heat Number With Certificate | 530-SP-M-0507 EN 10204 3.1 | Delivery Docket, Purchase Orders, Material Certificate | H R |  | H R |  | V
| Transfer Heat Numbers, Record And Maintain Materials Traceability | Verify Heat Numbers are on Materials | AS 1210, 530-SP-M-0507 | Material Tracebility Register | V |  | V |  | SU
FABRICATION
| Cut & Process Material To Given Dimension In Accordance With Drawings | Verify Dimensions | Detailed drawings AS 1210 530-SP-M-0507 | 06702-MP002-ITP-QM-001 | SU |  | SU |  | SU
| Verify Correct Nozzle Locations in Shell | Verify nozzle locations | Detailed drawings 530-SP-M-0507 | 06702-MP002-ITP-QM-001 | SU |  | SU |  | W
| Assemble External Components In Accordance With Drawings | Verify Dimensions | Detailed drawings AS 1210 530-SP-M-0507 | 06702-MP002-ITP-QM-001 | SU |  | SU |  | SU
| Check Fit Up And Dimensional Tolerances Prior To Welding | Verify Dimensions | Detailed drawings 530-SP-M-0507 | 06702-MP002-ITP-QM-001 | V |  | V |  | SU
WELDING
| Weld Forgings And Attachments To Shell | Visually Inspect Welds & Check Dimensions | DRAWINGS Weld Map 530-SP-M-0507 AS1210 AS3992 AS4458 | 06702-MP002-ITP-QM-001 | SU |  | SU |  | SU
| Assemble & Weld Internal Components In Accordance With Drawings | Visually Inspect Welds & Check Dimensions | DRAWINGS Weld Map 530-SP-M-0507 AS1210 AS3992 AS4458 | 06702-MP002-ITP-QM-001 | SU |  | SU |  | SU
| Prepare Production Test Plates | Check Material Heat Number With Certificate | PURCHASE ORDERS AND REQUISITIONS, AS 3992, AS 4458 | 06702-MP002-ITP-QM-001 | V |  | V |  | W
| Weld Vessel Circular Seams and Production Test Plates | Visually Inspect Welds From Weld Map And Check Dimensions | DRAWINGSAS 3992, AS 4458, 530-SP-M-0507 | 06702-MP002-ITP-QM-001 | SU H (PTP) |  | SU H (PTP) |  | SU W (PTP)
| Inspect Components For Weld Quality, Distortion And Dimensional Check / Tolerance After Welding | Visually Inspect Welds From Weld Map And Check Dimensions | DRAWINGSAS 3992, AS 4458, 530-SP-M-0507 | As-Built Drawings / Dimensional Report | H |  | H |  | SU
| Submit Production Test Plates and Material Certificates to NATA Laboratory for Testing | Verify that seams meet the requirements of AS1210 | AS 1210 Class 1 AS3992 | Production Test Plate Report | H V |  | H V |  | V R
| Stamp Lifting Lugs With WLL [SWL] (Total Vessel Dry Weight x 1.5) | Verify Against Approved Drawing | 530-SP-M-0507 | 06702-MP002-ITP-QM-001 | SU R |  | SU R |  | SU
INSPECTION AND TESTING
| Carry out NATA-endorsed Non Destructive Testing 100% RT/MPI Circular Seams, 100% MPI Nozzles, 100% RT Pipe Butts, 100% MPI Lifting attachments and all other welds. | Inspect Vessel & Test Welds using RT, UT, MPI. | AS 1210, AS 4037 class 1 530-SP-M-0507 | NDT REPORTS | H V |  | H V |  | V R
| Thoroughly Clean Vessel | Inspect Internal Cleanliness & Vessel Quality | 530-SP-M-0507 | 06702-MP002-ITP-QM-001 | R |  | R |  | SU
| Assemble Vessel and carry out NATA Endorsed Hydro-Testing. Drain on completion & dry thoroughly. | Prior To Testing Ensure Vessel Internals Are Clean | AS 1210, AS 4037 530-SP-M-0507 | NATA hydrotest report | H.W |  | H.W |  | H
SURFACE TREATMENT
| Pre-Inspect, Prepare And Despatch For Surface Treatment. | Inspect Vessel Internal For Cleanliness & Vessel Quality, Check For Sharp Edges. Ensure All Machined & Flange Faces Are Protected | DRAWINGS 530-SP-M-0507 530-SP-M-9602 | Paint Reports | SU W |  | SU W |  | SU
| Inspection On Return Of Vessel To Workshop From Surface Treatment Contractor | Inspect Paint And Vessel Quality | 530-SP-M-9602 | 06702-MP002-ITP-QM-001 | W |  | W |  | W
| Attach Nameplates To Vessel - Scan image beforehand | Verify Nameplate Contents & Inspect Installation Quality | DRAWINGS 530-SP-M-0507 | Nameplate Scan | R |  | R |  | V
PREPARATION FOR HANDOVER
| Carry Out Final Inspection - Issue Inspection Release Certificate | Check Presentation Of Workmanship, Check Documentation Complete & Sign Off ITP | Design drawings 530-SP-M-0507 530-SP-A-0002 | 06702-MP002-ITP-QM-001 Inspection Release Note | H |  | H |  | H
| Package Components And Attach Relevant Documentation For Delivery | Check Packing & Corrosion Protection | 530-SP-M-0507 530-SP-A-0002 | Delivery docket | SU W |  | SU W |  | SU
| Compile Manufacturers Data Report (Progressively Compiled) | Review On Completion | AS 1210 530-SP-M-0507 AS4458 | MDR | R |  | R |  | A, R