## Sheet1
Project: | [11 empty] | Date:
Contract No: | [11 empty] | Prepared By: | Peter Heyden
Project No: | [11 empty] | Reviewed By:
Client: |  | FMG | [9 empty] | Approved By:
Document No: | [11 empty] | Revision: | A
INSPECTION AND TEST PLAN | [7 empty] | Legend: W = Witness; R = Review; H = Hold; I = In-House; SU = Surveillance; S = Sub-Supplier; FM = Foreman; ENG = Engineer; SV = Surveyor; SC = Subcontractor; PT = Project Team; WS = Witness first time then random
ITP-MS002 STRUCTURAL STEEL (Surface Treatment)
Work Location: |  |  |  | Lot No: |  |  |  | Date Opened:
Item No: | Inspection Test Point / Activity | Responsible Person | Inspection Test / Method | Frequency | Controlling Procedure, Instruction or Specification | Acceptance Criteria | Verify Documents Record | Quality Control Activity | Conformance Check Inspection Point Acceptance |  |  | Comments
[9 empty] | Sub CON | Decmil | RTIO
1 | PRELIMINARIES
1.1 | ITP Development | PT, ENG,SC | Documentation Review | Prior to Commencement |  | Appendix D - CL2.2 | Quality Management Plan, Approved ITP | H
2 | Surface Treatment
2.1 | Coating Systems & Products in accordance with drawings specifications | PT, ENG, SC | Review | Prior to Commencement |  | Coating system complies with design and specs | Signed ITP | H
2.2 | Limits of areas/surfaces to be coated indicated & surrounding areas protected to prevent damage | SC | Review | Prior to Commencement |  | Appropriate protection provided to areas not to be painted | Signed ITP | W
2.3 | Surface prepared in accordance with specifications & supplier data whip blast Gal steel to achieve blast profile 25um | SC | Visual, Review | Each Lot |  | Surface prepared IAW Specification & Supplier data | Inspection report | WS
2.4 | Coating materials prepared & mixed adequately in accordance with manufactures recommendations | SC | Visual | Each Lot |  | Materials prepared IAW Suppliers data | Inspection report | W
2.5 | Surface Coatings applied in accordance with specified protection systems G3 SP118 50um interguard 251, apply finish coat of interfine 629 75um | SC | Visual | Each Lot |  | Surface Coatings applied IAW specified protection systems and schedule | Inspection report | R
2.6 | Coat finish acceptable: Surface smooth, free from holes and defects, thickness complies with specified protection systems | SC | Visual | Each Lot |  | Contain thickness IAW specifications and supplier data Tolerance of 0 to 20% Minimum DFT | Coating thickness report from subcontractor | W
2.7 | Items protected, stored, handled & Transported correctly | SC | Visual | Each Lot |  | Items protected,stored, hauled & transported IAW specifications | Signed ITP | R
2.8 | Lot Conforms | PT, SC | Review | Every despatch |  | Appendix F - CL2, 4.3 | Signed ITP | SU
3 | Documentation
3.1 | Verify all documentations are signed | PT, SC | Review | At Completion | ITP | - | - | R
3.2 | File all relevant documentation and reports in the MDR | PT, SC | Review | At Completion |  | Appendix D - CL2.3 | - | R

## Sheet2
No: 03 Hydraulic Services - Water & Sewerage (WSF)
AS/NZS 3500 (Set):2003 : Plumbing and drainage Set
AS 1180.5-1999 : Methods of test for hose made from elastomeric materials - Hydrostatic pressure
AS/NZS 1462.29:2006 : Methods of test for plastics pipes and fittings - Plastics piping and ducting systems - Determination of the long-term hydrostatic strength of thermoplastics materials in pipe form by extrapolation (ISO 9080:2003, MOD
AS 4809-2003/Amdt 1-2003 : Copper pipe and fittings - Installation and commissioning
AS/NZS 2566.2:2002 : Buried flexible pipelines - Installation

## Sheet3
CONCRETE STRUCTURE WORKS
Step | Heading | Description
1 | 12.6.1 | Excavation, compaction and backfill for Service

## Sheet4
Step | Heading | Description
1 | 1.2 | Description of Works
| b. | Services Infrstructure: water supply, water treatement, heating ventilation air-conditioning
| g | Potable water treatment system
| h | Wastewater treatment facilitypotable water storage
fire water storeage
carpark
pedestrian lighting