| Client: |  |  |  |  |  |  | Contract No: |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project: |  |  |  |  |  |  | Document No: |  |  |  |  |  |  |  | Revision: |  |  |  |  |
| Area/System No: |  |  |  |  |  |  | Area/System Description: |  |  |  |  |  |  |  |  |  |  |  |  |
| Reference Document |  |  |  |  |  | Controlling Document |  |  |  |  |  |  |  | Verifying Documents |  |  |  |  |  |
| No. | Title |  |  |  |  | No. |  | Title |  |  |  |  |  | No. |  |  | Title |  |  |
|  | BGER Project Quality Management Plan (PQMP) |  |  |  |  | AS 1554.1 |  | Structural Steel Welding Part 1 |  |  |  |  |  |  |  |  | Material certificates |  |  |
| AS 4100 | Steel Structure |  |  |  |  | AS 1674 |  | Safety in welding and allied process |  |  |  |  |  | BGER-QA-CHL-0001 |  |  | Material Inspection Report |  |  |
|  | Weld Procedure Specifications (WPS) |  |  |  |  | AS 2207 |  | Non Detructive Testing – UT of Fusion Welded Joints in Carbon and Low Alloy Steel |  |  |  |  |  |  |  |  | Tools calibration certificates |  |  |
|  | Welder Qualification Register (WQR) |  |  |  |  | AS 1657 |  | Fixed platforms, walkways, stairways and ladder – Design, construction and installation |  |  |  |  |  |  |  |  | Approved Lift Studies |  |  |
|  |  |  |  |  |  |  |  | Client’s welding specifications |  |  |  |  |  |  |  |  | Survey Report |  |  |
|  |  |  |  |  |  |  |  | AFC Dawings |  |  |  |  |  | BGER-QA-CHL-1001 |  |  | Structural Steel Erection Checklist |  |  |
|  |  |  |  |  |  | BGER-OP-WOR-0002 |  | Structural Bolting Installation Work Instruction |  |  |  |  |  | BGER-QA-CHL-1002 |  |  | Structural Bolting Checklist |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | NDT Report |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | BGER-QA-CHL-6001 |  |  | Grouting Checklist |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | BGER-QA-CHL-0002 |  |  | Coating & Surface Treatment Checklist |  |  |
| Legend |  |  |  |  |  |  |  |  |  |  | Approval and Change History |  |  |  |  |  |  |  |  |
| Verification Activity |  |  |  |  |  |  |  |  |  |  | Rev | Details |  | Date |  | Prepared by (BGER) |  |  | Client Approval (XXX) |
| H – Hold Point |  |  | Work shall not proceed past the Hold Point until released by the Organisation imposing the Hold Point. 48 hrs. notice required. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| W – Witness Point |  |  | An Inspection Point that may be witnessed by the Organisation imposing the Witness Point. 48 hrs. notice required. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| I – Inspection |  |  | Formal inspection activity to be undertaken and recorded. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| S – Surveillance |  |  | An activity that is subject to on-going monitoring |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R – Review |  |  | Review of text reports/records or other evidence of compliance. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Person (RP) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUP |  |  | Supervisor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| QR |  |  | Quality Representative (Project Engineer) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUR |  |  | Surveyor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NDTT |  |  | NDT Technician |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Item | Activity/Operations/Stage No. | Controlling Document/ Procedure | Standard, Spec, Drawing Ref or Acceptance Criteria | Verifying Document/ Report/ Certificate | Verification Activity by |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | BGER RP | BGER/ sign | Client/ sign |  |
| 1.0 | Approvals |  |  |  |  |  |  |  |
| 1.1 | Prepare BGER’s ITP and submit to Client for Approval | PQMP | ITP | Approved ITP | QR | H | H |  |
| 1.2 | Submit and obtain approval for Weld Procedure Specifications and Welder Qualifications | PQMP | AS 1554.1 | Approved WPS and WQR | QR | H | H |  |
| 1.3 | Confirm all critical and heavy Lifts are identified. Prepare Lift Studies to suit and submit to Client for Approval. | PQMP | ITP | Approved Lift Studies | QR | H | H |  |
| 2.0 | Material Receipt |  |  |  |  |  |  |  |
| 2.1 | Check material for damage due to delivery and fabrication defect | PQMP | AFC Drawing, Delivery Packing List | Delivery Packing List, Material Inspection Report | QR | I, R | R |  |
| 2.2 | Confirm correct material received | PQMP | Project Structural Steel drawings and specs | Material Certificates | QR | I, R | R |  |
| 2.3 | Check that correct quantities and dimensions of material and welding consumables are delivered | PQMP | AFC Drawing, Bill of Material | Material Inspection Report, Welding Consumables material certificates | QR | I, R | R |  |
| 3.0 | Survey and Equipment set up |  |  |  |  |  |  |  |
| 3.1 | Confirm the Relative Level (RL) and coordinates for the steel structures to be erected are correct. | PQMP | AFC Layout Drawings Survey control points | Survey Report | SUR | I, H | R |  |
| 3.2 | Mark out the location and orientation of the steel structures. | PQMP | AFC Layout Drawings Survey control points | Survey Report | SUR | I | R |  |
| 3.3 | Check and confirm that all owned/hired required plants and tools are available and calibrated (where required) to suit. | PQMP | Project Execution Plan | Calibration Certificates | QR | I | R |  |
| 3.4 | Area handover and acceptance | PQMP | ITP | Contract Requirement | QR | H | H |  |
| 4.0 | Structural Steel Erection |  |  |  |  |  |  |  |
| 4.1 | Setup crane and lift structure in position. Confirm layout of the structural steel to be erected. Visual inspection of fit up for welding. | PQMP | AS 4100, AFC Drawings, Client’s specs | Structural Steel Erection Checklist | SUP | I, R | S | If BGERrary bracing is required, Client’s approval on the bracing may be required. |
| 4.2 | Welding to conform with standards and Client’s specs. | WPS, WQR | AS 1554.1, Client’s specs | Weld Map | QR | I | S |  |
| 4.3 | NDT of welds | AS 4100 | AS 1554.1, AS 2207 | NDT Report | NDTT | H | R |  |
| 4.4 | Confirm that correct tension/ torque are applied for all bolted connections | PQMP | AS 4100, AFC drawings, Client’s specs, Bolting Work Instruction | Structural Steel Erection Checklist, Bolting Checklist | QR | I, R | S |  |
| 4.5 | Confirm that correct shimming of base plates and alignment prior to grouting (where grouting is required) | PQMP | AS 4100, AFC Drawings, Client’s specs | Structural Steel Erection Checklist | QR | I, R | S |  |
| 4.6 | Confirm correct installation of handrails | PQMP | AS 1657, AFC Drawings, Client’s specs | Structural Steel Erection Checklist | QR | I, R | S |  |
| 4.7 | Confirm correct installation of grating including sufficient fixings | PQMP | AS 1657, AFC Drawings, Client’s specs | Structural Steel Erection Checklist | QR | I, R | S |  |
| 4.8 | Confirm Correct Installation of access ways (stairways, ladders) | PQMP | AS 1657, AFC Drawings, Client’s specs | Structural Steel Erection Checklist | QR | I, R | S |  |
| 4.9 | Final Survey of Steel Structures | PQMP | AS 4100, AFC Drawings, Client’s specs | Survey Report | SUR | I, H | H |  |
| 4.10 | Confirmed grouting is installed to specifications. | PQMP | AS 4100, AFC Drawings, Client’s specs | Grouting Checklist | QR | I, R | S | Sub-contractor to supply detailed ITP |
| 5.0 | Surface Treatment |  |  |  |  |  |  |  |
| 5.1 | Painting & Surface Treatment | PQMP | Client’s specs | Coating & Surface Treatment Checklist | QR | W | R | Sub-contractor to supply detailed ITP |
| 6.0 | Mechanical Completion |  |  |  |  |  |  |  |
| 6.1 | Confirm complete compilation of all the Inspection & Test Records by discipline/system. This compilation will be added to the dossier for System/Area Mechanical Completion which when completed with all disciplines and other works will be submitted to Client for approval. | PQMP | Client’s specs | Compilation of Inspection & Test Records | QR | R | S |  |
| 7.0 | Quality Documents |  |  |  |  |  |  |  |
| 7.1 | Completion of MDR | PQMP | Client’ Specs | MDR progressive review and sign off | QR | R | R |  |