## Sheet1
ITP Discipline |  | Structural Steel Supply and Fabrication WIP |  | Project Area | Yamarna Gas Pipeline & Stations
Project Title |  | Design and Supply of Yamarna Gas Skids |  | Revision | B
Primero Document No. |  | 06702-ITP-ST-001 |  | Date | 2017-10-20
Client |  | APA Group |  | Prepared | R. O’Callaghan
Client Document No. |  | YGP-020-ITP-QM-0003 |  | Approved | B. Zlnay
H = HOLD POINT |  | V = VISUAL INSPECTION | R = REVIEW & COMMENT | D = DIMENSIONAL INSPECTION |  | WR = WITNESS @ RANDOM
W = WITNESS POINT |  | M = MONITOR ON A RANDOM BASIS | A = APPROVE | S = SUBMIT DOCUMENT TO CLIENT
REF | INSPECTION AND TEST ACTIVITY | APPLICABLE DOCUMENT OR PROCEDURE ETC. | ACCEPTANCE CRITERIA | VERIFYING DOCUMENT | INSPECTION AND VERIFICATION
[5 empty] | Primero |  | Client |  | 3RD Party Inspection
[5 empty] | Activity | Signature | Activity | Signature | Activity | Signature
1 | SPECIFICATIONS
1.1 | Review Scope of Work | YGP-SOW-A-0001 | Not Applicable | Contract Document | R |  | R
1.2 | Review Design | Packaged Equipment Specification, YGP-SP-A-0002 | YGP-SOW-A-0001 | Design Approval, VDS | R |  | R
1.3 | Review Drawings | AFC Drawings | Drawings | AFC Drawings | S |  | R
2 | APPROVALS
2.1 | Submit Project Documentation, ITP, NDE Procedures, Coating Procedures | ITP, NDE Procedures | 530-SP-S-0004 AS1554.1 530-SP-M-9602 | Approved ITP’s NDE Procedures, Coating Procedure | H |  | A, H, R
2.2 | Submit Weld Procedure Specifications & Qualifications | YGP-020-WPS-QM-0004_2.0 YGP-020-WPS-QM-0005_2.0 YGP-020-WPS-QM-0006_1.0 YGP-020-WPS-QM-0007_1.0 YGP-020-WPS-QM-0008_1.0 YGP-020-WPS-QM-0009_1.0 | AS1554.1-SP | Approved WPSs & WPS Register | H |  | A, H, W
2.3 | Submit Welder Qualifications | Welder Qualification Reports & register | AS1554.1-SP | Approved Welder Qualifications & Welder Qualifications Register | H |  | A, H, W
3 | MATERIALS
3.1 | Monitor Incoming Materials (New) and Client supply | Design drawings; 530-SP-S-0004, Materials Management Procedure YGP-020-PL-QM-0001 | 530-SP-S-0004 | Signed Delivery Dockets; Material Certificates, Inspection Certificates | R |  | WR
3.2 | Material Traceability | 530-SP-S-0004, Materials Management Procedure YGP-020-PL-QM-0001 | Materials Specifications, EN10204 3.2 | Traceability records for structural works & material certificate register | R |  | M
4 | MATERIALS PREPARATION
4.1 | Mark materials for cutting & weld preparation. Dimensional check. | Design drawings | 530-SP-S-0004 Shop drawings | 530-SP-S-0004, design and shop drawings | R, D |  | M
4.2 | Prepare controlled/cut materials for fabrication | Material Control Procedure | 530-SP-S-0004 AS4100 | Cutting list | R |  | M
4.3 | Consumables Control | Consumable Control Procedure | 530-SP-S-0004 | Manufacturers Recommendations & Consumables register | R |  | M
5 | FABRICATION
5.1 | Assemble material components as per drawing. | Project Execution Plan - YGP-020-PL-A-0001, General Arrangement Drawings | 530-SP-S-0004 AS 1554.1-SP | IFC Drawings | R |  | M
5.2 | Dimensional check & fit up inspection prior to welding | Dimensional check Procedure | 530-SP-S-0004 AS 1554.1-SP | 530-SP-S-0004, fabrication detail drawings, checklists | R, D |  | M
5.3 | Welding of assembled components | Approved WPS’s & Welder Qualifications | 530-SP-S-0004 AS 1554.1-SP | Traceability documentation - YGP-020-SCH-A-0003 | R |  | M
5.4 | Ongoing visual weld inspection of all welded components. | Project Execution Plan - YGP-020-PL-A-0001, General Arrangement Drawings, WPS | 530-SP-S-0004 AS 1554.1-SP | Client design and shop drawings, checklists, YGP-020-SCH-A-0003 | R |  | M
6 | INSPECTION & TESTING
6.1 | NDE in accordance with approved drawings, specifications | Subcontractor NDE Procedures (Document # TBA) | 530-SP-S-0004 AS/NZS 1554.1-SP | Certified NATA reports, welds maps & NDE traceability records | H |  | WR, R
6.2 | Weld repairs | Subcontractor NDE Procedures (Document # TBA) Repair Procedure (Document # TBA) | 530-SP-S-0004 AS 1554 | Certified NATA reports, weld maps & NDE traceability records, repair records | H |  | H
6.3 | Perform final inspection after welding fabrication components: Visual, dimensional, distortion checks, etc. | Dimensional checks | 530-SP-S-0004 AS4100 AS/NZS1554.1-SP | 530-SP-S-0004, client design and shop drawings, As-builts | H, V, D |  | H, V, D
7 | SURFACE TREATMENT
7.1 | Complete applicable surface treatment | Coating Subcontractor Procedure, Coating Subcontractor ITP | Surface Treatment and Finishes 530-SP-M-9602 | Surface Treatment Records | R |  | WR, R
8 | DESPATCH
8.1 | Review completed ITP | 06702-ITP-ST-002 | Not applicable | Approved ITP | R, R |  | R, R
8.2 | Preparation & packaging for transport & load out to site | Packing, preservation and transportation procedure YGP-020-PR-A-0005 | 530-SP-A-0002 | Delivery Documentation & inspection release certificates, Load Hazard Analysis, Shipping Details and Packing List, photos, Appendix F of Contract | W, H |  | W, H
8.3 | Final Inspection | YGP-SOW-A-0001, 530-SP-P-0002, YGP-SP-A-0002 | 530-SP-A-0002 | Delivery documentation, Inspection release certificates | W, H |  | W, H
8.4 | Delivery to Site | Inspection release – review & acceptance | 530-SP-A-0002 | Approved ITP | W, H |  | W, H
9 | VERIFICATION
9.1 | Punchlisting | AFC Drawings, YGP-SOW-A-0001 | AFC Drawings, YGP-SOW-A-0001 | Completed Client Punchlist | H |  | H